## Project_List
Region | CLUB | FMSS Location Number | FMSS Asset # | FMSS WO # | PST WO# | PMIS # | Component | ATC Project # | WORK TYPE | ASSET TYPE | DISTRICT | LOCATION | DEFICIENCY | Trail Assessment "AT ID" (indicate ID number, or range of IDs, project will address) | PROJECT DESCRIPTION | LIST ADDITIONAL MATERIALS AND/OR SERVICES NEEDED | ITEM | QTY | U.O.M | NPS Estimate | NPS Request Amount | ATC Direct Project | ATC Indirect (23.64%) | CREW | CREW WEEKS | YEAR | CLUB PRIORITY | FUND TYPE | NPS FUNDING Status | ENVIRO COMPLIANCE LEAD AGENCY? | PEPC # | PROJECT STATUS | CLUB ESTIMATE | Seg./Tract # | COMMENTS/OTHER: | LAST UPDATED | UPDATED BY: | CHANGES
2. MA | 1. NYNJTC | 77139 | 384798 | 896082 | N/F | N/F |  |  | DM | B | Dutchess-Putnam | E. Fishkill (Hosner Mtn Road) | Bridge washout candidate |  | Repair Bridge |  |  |  |  | NEED | 1500 | 1213.1996 | 286.8004 |  |  | 2013 | M | RR-T | Not Requested |  |  |  | 1500 |  |  | 2013-02-25 | JCB | WAS 2010 MOVE to 2012
2. MA | 1. NYNJTC | 77139 | 297432 | 712382 | 711342 | WAS 62416, NEED NEW |  |  | CI | CR | Dutchess-Putnam | Schaghticoke MT (265) | Illegal ATV use on A.T. lands. |  | Install boulder closure. | Contract services. | Build/Add: Gate-each | 2 | EA | 2893.8 | 2900 | 2345.5192 | 554.4808 | No Crew | 0 | 2013 | M | RR-S | NEED |  |  |  | 3000 | 265 | Wait and watch. | 2006-11-12 | RSR | WAS 2005 MOVE to 2013
2. MA | 1. NYNJTC | 101907 | N/A | N/A | N/A | N/A |  |  | RM | WS | Dutchess-Putnam | Messerschmidt | Need monthly testing of total coliform |  | test water systems for TC monthly | Contract services | Water Samples | 12 | EA | NEED | 600 | 485.2798 | 114.7202 | No Crew | 0 | 2013 | H | Base | NEED |  |  |  | 360 |  |  | 2013-02-25 | JCB | Club estimate was changed from 300 to 360
2. MA | 1. NYNJTC | 101907 | N/A | N/A | N/A | N/A |  |  | RM | WS | Dutchess-Putnam | Wiley | Need monthly testing of total coliform |  | test water systems for TC monthly | Contract services | Water Samples | 12 | EA | NEED | 600 | 485.2798 | 114.7202 | No Crew | 0 | 2013 | H | Base | NEED |  |  |  | 360 |  |  | 2013-02-25 | JCB | Club estimate was changed from 300 to 360
2. MA | 1. NYNJTC | 101908 | N/A | N/A | N/A | N/A |  |  | RM | WS | Dutchess-Putnam | Morgan Stewart | Need monthly testing of total coliform |  | test water systems for TC monthly | Contract services | Water Samples | 12 | EA | NEED | 600 | 485.2798 | 114.7202 | No Crew | 0 | 2013 | H | Base | NEED |  |  |  | 360 |  |  | 2013-02-25 | JCB | Club estimate was changed from 300 to 360
2. MA | 1. NYNJTC | 101909 | N/A | N/A | N/A | N/A |  |  | RM | WS | Dutchess-Putnam | RPH Cabin | Need monthly testing of total coliform |  | test water systems for TC monthly | Contract services | Water Samples | 12 | EA | NEED | 600 | 485.2798 | 114.7202 | No Crew | 0 | 2013 | H | Base | NEED |  |  |  | 360 |  |  | 2013-02-25 | JCB | Club estimate was changed from 300 to 360
2. MA | 1. NYNJTC | 77139 | 297432 | 5121049 | 5121052 | 164093 | A |  | CI | T | Dutchess-Putnam | Pawlings Nature Preserve | wet, eroded trail |  | Install I mile of puncheon |  | Build/AddPuncheon -lf | 5000 | LF | 45600 | 25000 | 20219.9935 | 4780.0065 | SCA | 12 | 2013 | M | PLC | NEED | [5 empty] | In bad shape in 2009, club would like to see done sooner than 2015 | 2010-01-27 | JPH | WAS 2008 MOVE to 2015 - MOVE Earlier
2. MA | 1. NYNJTC | 77139 | N/F | N/F | N/F | N/F |  |  |  |  | Dutchess-Putnam | Between Nuclear Lake & Rt 55 | Better utilize Nuclear Lake parcel |  | Extend yellow loop trail |  | Build/AddTrail: New -lf | 2600 | LF |  |  |  |  | No Crew |  | 2013 | H |  |  | APPA |  | NEW PROJECT |  | 269-18 |  | 2013-02-25 | JCB | NEW PROJECT
2. MA | 1. NYNJTC | 101907 | N/A | N/A | N/A | N/A |  |  | RM | WS | Dutchess-Putnam | Messerschmidt | Need monthly testing of total coliform |  | test water systems for TC monthly | Contract services | Water Samples | 12 | EA |  |  | 0 | 0 | No Crew | 0 | 2014 | H | Base | NEED |  |  |  | 360 |  |  | 2013-02-25 | JCB | Club estimate was changed from 300 to 360
2. MA | 1. NYNJTC | 101907 | N/A | N/A | N/A | N/A |  |  | RM | WS | Dutchess-Putnam | Wiley | Need monthly testing of total coliform |  | test water systems for TC monthly | Contract services | Water Samples | 12 | EA |  |  | 0 | 0 | No Crew | 0 | 2014 | H | Base | NEED |  |  |  | 360 |  |  | 2013-02-25 | JCB | Club estimate was changed from 300 to 360
2. MA | 1. NYNJTC | 101908 | N/A | N/A | N/A | N/A |  |  | RM | WS | Dutchess-Putnam | Morgan Stewart | Need monthly testing of total coliform |  | test water systems for TC monthly | Contract services | Water Samples | 12 | EA |  |  | 0 | 0 | No Crew | 0 | 2014 | H | Base | NEED |  |  |  | 360 |  |  | 2013-02-25 | JCB | Club estimate was changed from 300 to 360
2. MA | 1. NYNJTC | 101909 | N/A | N/A | N/A | N/A |  |  | RM | WS | Dutchess-Putnam | RPH Cabin | Need monthly testing of total coliform |  | test water systems for TC monthly | Contract services | Water Samples | 12 | EA |  |  | 0 | 0 | No Crew | 0 | 2014 | H | Base | NEED |  |  |  | 360 |  |  | 2013-02-25 | JCB | Club estimate was changed from 300 to 360
2. MA | 1. NYNJTC | 76726 | N/F | N/F | N/F | N/F |  |  | DM | CR | Dutchess-Putnam | Shenandoah Camp Site | Deteriorated. Old chain link fence |  | Remove |  |  |  |  | NEED | 500 | 404.3999 | 95.6001 | No Crew | 0 | 2015 | L |  | Not Requested | APPA |  | NEED |  |  | Garden used to be enclosed by fence - 2008 or 2009 | 2013-10-20 | JCB | Updated year from 2012 to 2015
2. MA | 1. NYNJTC | 95592 | N/A | N/F | N/F | N/F |  |  | DM | P | Dutchess-Putnam | RPH and Shenandoah campsite (273-01, 13) | Privies aging, filling up |  | Rehab privies & convert to moldering type | [6 empty] | 0 | 0 |  |  | 2015 | H |  | NEED |  |  | NEED | 1500 |  |  | 2013-10-20 | JCB | Updated year from 2012 to 2015
2. MA | 1. NYNJTC | 89651, 811221 | N/A | 896078 | 5095328 | 163981 |  |  | Demo | BU | Dutchess-Putnam | Tegzes/Yegella (268-33) | Incidentally acquired structures |  | Remove structure and restore tract to natural state. | Contract removal of structure | Structure | 2 | EA | 10193 | 10193 | 8244.0958 | 1948.9042 | No Crew | 0 | 2015 | L | RR-Demo | Requested |  |  | In Planning | on demo list | 268-33 | …; delay until Dennis SUP has been renewed | 2006-11-12 | RSR | WAS 2005
2. MA | 1. NYNJTC | 81199, 89653 | N/A | 896076 | 5095328 | 163981 |  |  | DM | BU | Dutchess-Putnam | Messerschmitt (273-13) | Incidentally acquired structures |  | Remove structure and restore tract to natural state. | Contract | Structure | 2 | EA | 21136 | 21136 | 17094.7913 | 4041.2087 | No Crew | 0 | 2015 | L | RR-Demo | Requested | APPA | NEED | Awaiting Funding | Would like to do in 2008 | 273-13 | vandalism issues. More incidents in 2008 & 2009. Combine with lines 27 and 37 for efficiency? | 2010-07-23 | JDR | Was 2009, moved to 2012
2. MA | 1. NYNJTC | 81121 | N/A | 896078 | N/F | N/F |  |  | Demo | BU | Dutchess-Putnam | Hurds Corners, Dover Oak (Yeggela?) (268-38 | Dilapidated springhouse foundation/retention basin and pumphouse foundation. |  | Remove springhouse foundation/reservoir and pumphouse foundation. | Contract demolition. |  |  |  | 0 | 0 | 0 | 0 | No Crew | 0 | 2015 | M | RR-Demo | NEED |  |  |  | $5K | 268-38 | On Demo List??? | 2010-07-23 | JDR | MOVED to 2014
2. MA | 1. NYNJTC | 81152 | N/A | 896043 | 5095328 | 163981 |  |  | Demo | BU | Dutchess-Putnam | Guardia (271-34) along Hosner Mtn Rd | Incidentally acquired structures |  | Remove structure and restore tract to natural state. | Contract removal of structure | Structure | 1 | EA | 8347 | 8347 | 6751.0514 | 1595.9486 | No Crew | 0 | 2015 | L | RR-Demo | Requested | APPA |  | NEED | 1000 | 271-34 | Much of area cleaned up years ago by vols. Masonary mat'l remains to be removed (was 2010, moved to 2015) | 2009-02-19 | JPH
2. MA | 1. NYNJTC | 77139 | 297432 | [5 empty] | CI | T | Dutchess-Putnam | Hoyt Road (266-39) | Trail co-aligned with road and vehicular traffic. Trail not in optimal location. |  | Relocate Trail off road | Acquire approximately 4.32 acres, upgrade easement to relocate Trail approximately 1/2 mile. | Build/AddTrail: New -lf |  |  | 0 | 0 | 0 | 0 | No Crew | 0 | 2015 | M |  | Not Requested |  |  | NEW PROJECT | 10000 | 266-39 | NPS owns scenic easement need to up grade to R-O-W | 2010-01-14 | JPH | Was 2004 MOVE to 2015
2. MA | 1. NYNJTC | 77139 | 297432 | [5 empty] | CI | T | Dutchess-Putnam | Harlem Valley Psych Center (267-03, 24) | Illegal ATV use on A.T. lands. |  | Install boulder and gate closures. | Contract services. | Build/Add: Gate-each | 2 | EA | 2893.8 | 2893.8 | 2340.5047 | 553.2953 | No Crew | 0 | 2015 | H | CM | Not Requested |  |  | UNKNOWN | 3000 | 267-03, 24 | Massive residential and commercial development adjacent to trail lands to start in 2010 | 2010-01-10 | JPH | WAS 2004 MOVE to 2008 MOVE to 2015
2. MA | 1. NYNJTC | N/A | [6 empty] | CI | PL-bb | Dutchess-Putnam | North side of Route 301 crossing (274) | No public information at major parking area |  | Rebuild and use former Nuclear Lake parking lot bulletin board | Build bulletin board using design of other recent boards | [5 empty] | 0 | 0 | SCA | 1 | 2015 | M | PLC | Not Requested |  |  | Not on plan | 300 |  |  | 2010-01-14 | JPH
2. MA | 1. NYNJTC | 77139 | 297432 | N/F | N/F | N/F |  |  | DM | T | Dutchess-Putnam | Trail south of West Dover Rd. (City Route 20) | Early signs of rot in puncheon |  | Replace puncheon and substructure | Plastic posts and planking |  | 30 | LF |  |  | 0 | 0 |  |  | 2015 | M |  | NEED | [6 empty] | 2009-02-16 | JPH | WAS 2009 MOVE to 2015
2. MA | 1. NYNJTC | 95592 | N/A | N/F | N/F | N/F |  |  | CI | P | Dutchess-Putnam | RPH Shelter site (273-01) | Privy gets heavy use |  | Modify privy to use pumpable tank | [5 empty] | 5000 | 4043.9987 | 956.0013 |  |  | 2015 | M | RR-OS | NEED |  |  |  | 5000 |  |  | 2009-02-20 | JPH | Year - Move to 2015 from 2012
2. MA | 1. NYNJTC | 81501 | 375124 | 9299928 |  |  |  |  | RM | OA | Dutchess-Putnam | I-84 overlook (271-22) | Natural succession is taking over the open meadow. |  | Mow field to maintain meadow. | contract mower/ SUP Holder Charlie Dennis to mow approximately 20 acres | Brush mowing, tractor w/rotary mower | 20 | AC | 4880 | 1200 | 970.5597 | 229.4403 | No Crew | 0 | 2015 | H | CM | NEED | [5 empty] | Cyclic, was done in 2006 and 2009 ($800) | 2010-01-14 | JPH | NEW PROJECT
2. MA | 1. NYNJTC | 97586 | 366127 | [5 empty] | DM | ECBS | Dutchess-Putnam | Various | Missing NPS boundary monuments |  | Replace missing NPS boundary monuments | [6 empty] | 0 | 0 |  |  | 2015 | H |  | NEED |  |  |  | Approx 20 monuments at $700 ea |  |  | 2008-04-09 | JPH | NEW PROJECT
2. MA | 1. NYNJTC | 97586 | 366127 | [5 empty] | DM | ECBS | Dutchess-Putnam | (1) 270-21 (ROW) (2) 270-22 (3) 0.87ac near Gardiner Hollow Rd (4) ATC property near Hosner Mtn Rd (5) 0.43 ac near Back Ct; Parcel exchange for 269-29 | Parcels never surveyed |  | Survey parcels | [6 empty] | 0 | 0 |  |  | 2015 | H |  | NEED | [5 empty] | Added another parcel - item #6 under Location. (Do we need to add this parcel in FMSS?) | 2013-02-25 | JCB | Added parcel to location
2. MA | 1. NYNJTC | 88969 | N/A | N/F | N/F | N/F |  |  | CI | BU | Dutchess-Putnam | Nuclear Lake [269-18] | Need more space for storage of club tools and supplies. Current space conflicts with Nuclear Lake caretaker's use |  | Build shed | [6 empty] | 0 | 0 |  |  | 2015 | H |  | NEED |  |  |  | 7000+ |  | Combine with 2011 project | 2010-01-14 | JPH | NEW PROJECT
2. MA | 1. NYNJTC | 77139 | 297432 | N/F | 836483 | 126223 | A |  | CI | T | Dutchess-Putnam | Nuclear Lake | Road to Nuke Lake not handicap accessible |  | Provide Access through gate near caretaker's house | [6 empty] | 0 | 0 | No Crew | 0 | 2015 | M |  | Not Requested |  |  |  | 500 |  | Gate across entrance road does not allow wheelchairs through | 2009-02-16 | JPH | NEW PROJECT
2. MA | 1. NYNJTC | 101907 | N/A | N/A | N/A | N/A |  |  | RM | WS | Dutchess-Putnam | Messerschmidt | Need monthly testing of total coliform |  | test water systems for TC monthly | Contract services | Water Samples | 12 | EA |  |  | 0 | 0 | No Crew | 0 | 2015 | H | Base | NEED |  |  |  | 360 |  |  | 2013-02-25 | JCB | Club estimate was changed from 300 to 360
2. MA | 1. NYNJTC | 101907 | N/A | N/A | N/A | N/A |  |  | RM | WS | Dutchess-Putnam | Wiley | Need monthly testing of total coliform |  | test water systems for TC monthly | Contract services | Water Samples | 12 | EA |  |  | 0 | 0 | No Crew | 0 | 2015 | H | Base | NEED |  |  |  | 360 |  |  | 2013-02-25 | JCB | Club estimate was changed from 300 to 360
2. MA | 1. NYNJTC | 101908 | N/A | N/A | N/A | N/A |  |  | RM | WS | Dutchess-Putnam | Morgan Stewart | Need monthly testing of total coliform |  | test water systems for TC monthly | Contract services | Water Samples | 12 | EA |  |  | 0 | 0 | No Crew | 0 | 2015 | H | Base | NEED |  |  |  | 360 |  |  | 2013-02-25 | JCB | Club estimate was changed from 300 to 360
2. MA | 1. NYNJTC | 101909 | N/A | N/A | N/A | N/A |  |  | RM | WS | Dutchess-Putnam | RPH Cabin | Need monthly testing of total coliform |  | test water systems for TC monthly | Contract services | Water Samples | 12 | EA |  |  | 0 | 0 | No Crew | 0 | 2015 | H | Base | NEED |  |  |  | 360 |  |  | 2013-02-25 | JCB | Club estimate was changed from 300 to 360
2. MA | 1. NYNJTC | 72465 | N/A | N/A | N/A | N/A |  |  | RM | B | Dutchess-Putnam | Various | Bridge inspections |  | Arrange for engineer to inspect major foot bridges (e.g. RPH Shelter, Swamp River) | [6 empty] | 0 | 0 |  |  | 2015 | H |  | NEED |  |  |  | Unknown |  | Should be cyclic process; probably 4 or 5 major bridges involved | 2009-02-16 | JPH | NEW PROJECT
2. MA | 1. NYNJTC | 76726 | N/F | N/F | N/F |  |  |  | DM | CR | Dutchess-Putnam | Shenandoah Camp Site | Access Road impassable |  | Re-grade Road |  |  |  |  | NEED | 1500 | 1213.1996 | 286.8004 | No Crew | 0 | 2016 | L |  | Not Requested |  |  | NEED |  |  |  | 2013-10-20 | JCB | Updated year from 2012 to 2016
2. MA | 1. NYNJTC | 77139 | 297432 | 9320511 | 9323535 | 191064 |  |  | DM | T | Dutchess-Putnam | 268-15 & 16 north of DC 20 | Rotting puncheon |  | Replace deteriorating puncheon |  |  | 300 | LF |  | 5750 | 4650.5985 | 1099.4015 | Mid-Atlantic | 1 | 2016 | H | RR-T | Requested |  |  |  | 1000 |  | Was 2015 - move to 2016 | 2012-01-26 | JDR | REQUESTED
2. MA | 1. NYNJTC | 77139 | 297432 | 5121049 | 5121052 | 164093 | A |  | DM | T | Dutchess-Putnam | Pawling Nature Preserve | Rotting puncheon |  | Replace deteriorating puncheon | [6 empty] | 0 | 0 | No Crew | 0 | 2016 | H |  | NEED |  |  |  | 1000 |  | Was 2015 move to 2016 | 2009-02-20 | JPH | NEW PROJECT
2. MA | 1. NYNJTC | 77139 | 297432 | 9320601 | 9323535 | 191064 |  |  | DM | T | Dutchess-Putnam | S. of Morgan Stewart Shelter (270-07) | Erosion |  | Install steps |  |  | 800 | LF |  | 4750 | 3841.7988 | 908.2012 | Mid-Atlantic | 1 | 2016 | H | RR-T | Requested | [5 empty] | Was 2015 - move to 2016 | 2012-01-26 | JDR | REQUESTED
2. MA | 1. NYNJTC | N/A | N/A | N/A | N/A | N/A |  |  | CI | CR | Dutchess-Putnam | Putnam County and Nuclear Lake | No Cultural Signage |  | Design and produce historic material for bulletin boards |  |  |  |  | NEED | 500 | 404.3999 | 95.6001 | No Crew | 0 | 2016 | M |  | Not Requested |  |  | UNKNOWN |  |  | Need OK from NPS for inoculation and hut sites | 2010-01-14 | JPH | Club Priority, NPS Funds?
2. MA | 1. NYNJTC | N/A | N/A | N/A | N/A | N/A |  |  | CI | I | Dutchess-Putnam | Revolutionary War inoculation site | Lack of interpretive information |  | Install interpretive information | [8 empty] | No Crew | 0 | 2016 | M |  | NEED | APPA |  | NEW PROJECT |  |  |  | 2010-01-14 | JPH | NEW PROJECT
2. MA | 1. NYNJTC | 72465 | N/A | N/F | N/F | N/F |  |  | CI | S | Dutchess-Putnam | Morgan Stewart Shelter (270-22),Wiley Shelter, RPH Cabin, Shenandoah Campsite | Bear seen in vicinity |  | Install food storage | [8 empty] | No Crew | 0 | 2016 | M |  | NEED | APPA |  | NEW PROJECT |  |  |  | 2013-02-25 | JCB | Added Wiley Shelter, RPH Cabin, Shenandoah Campsite to the project.
2. MA | 1. NYNJTC | 77139 | 297432 | N/F | N/F | N/F |  |  | DM | T | Dutchess-Putnam | Sweetman Road | Deteriorating puncheon |  | Relocate Trail | [10 empty] | 2016 | H |  | NEED | APPA |  | NEW PROJECT |  |  |  | 2013-02-25 | JCB | Changed from replace puncheon to relocate trail
2. MA | 1. NYNJTC | 72465 | 297432 | 5110291 | 5110411 | 164067 | A |  | DM | PL | Dutchess-Putnam | Nuclear Lake (269-18) | Emergency access to caretaker house and lake can be blocked by parked cars |  | Redesign parking area | [10 empty] | 2016 | H |  | NEED | APPA |  | NEW PROJECT |  |  |  | 2010-01-14 | JPH | NEW PROJECT
2. MA | 1. NYNJTC | 72465 | N/A | N/F | N/F | N/F |  |  | DM | BU | Dutchess-Putnam | Yegalla barn (268-33) | Structural deficiencies, including floor joists |  | Evaluate and repair | [10 empty] | 2016 | H |  | NEED | APPA |  | NEW PROJECT |  | 268-33 |  | 2010-01-14 | JPH | NEW PROJECT
2. MA | 1. NYNJTC | 95200 | N/F | N/F | N/F | N/F |  |  | DM | CR | Dutchess-Putnam | Morgan Stewart (270-22) | Illegal ATV use on A.T. lands |  | Install iceberged boulders | Contract services |  | 2 | EA |  |  | 0 | 0 | No Crew | 0 | 2016 | H | CM | NEED | APPA | CE-PA |  |  |  | Needs lower gate landowner permission | 2010-01-14 | JPH | NEW PROJECT
2. MA | 1. NYNJTC | 95355 & 95200 | N/A | N/A | N/A | N/A |  |  |  |  | Dutchess-Putnam | RPH Cabin & Morgan Stewart Shelter | Aging roof |  | Reshingle | [8 empty] | No Crew |  | 2017 | H |  |  | APPA |  | NEW PROJECT |  |  |  | 2013-02-25 | JCB | NEW PROJECT
Note on F1: Bundy, Jessica: Parent WO
Note on O1: "AT ID" is the unique ID number assigned to each deficiency found during the Trail Assessment. The "AT ID" can be found on the Google Earth Trail Assessment Disc provided to each club. The first letters of the AT ID indicate what type of deficiency: TR = Tread CS=Campsite SH=Shelter TO=Toilet (Privy) PK=Parking CR=Corridor BR=Bridge

## Completed_Projects
Region | CLUB | FMSS Asset Number | FMSS Equipment # | FMSS WO # | PST WO# | PMIS # | Component | ATC Project # | Work Type | ASSET TYPE | DISTRICT | LOCATION | DEFICIENCY | Trail Assessment "AT ID" (indicate ID number, or range of IDs, project will address) | PROJECT DESCRIPTION | LIST ADDITIONAL MATERIALS AND/OR SERVICES NEEDED | ITEM | QUANTITY | U.O.M | NPS Estimate | NPS Request Amount | ATC Direct Project | ATC Indirect (17.53%) | CREW? | CREW WEEKS | YEAR | Club Priority | Fund Type | NPS Funding Status | ENVIRO COMPLIANCE LEAD AGENCY? | PEPC # | Project Status | Club Estimate | Seg./Tract # | Comments/Other | Last Updated | Updated By | CHANGES
2. MA | 1. NYNJTC | 77139 |  | n/a |  |  |  |  | Capital | T | Dutchess-Putnam | Long Hill Road (273-09) | Illegal dumping on A.T. lands. |  | Install boulder closure. | Purchase and install boulder closures | Build/Add: Gate-each | 1 | EA | 1446.9 | 1446.9 |  |  | No Crew | 0 | 2004 | M | CM |  |  |  | COMPLETE | 1000 | 273-09 | E. Fishkill supplied boulders | 2008-04-09 | JPH | Project Status, Comments
2. MA | 1. NYNJTC | 81346 | 280957 | 895255 | 711342 | 62416 |  |  | DM | BU | Dutchess-Putnam | Nuclear Lake | roof is in disrepair |  | replace house and garage roof, gutters and leak damaged sheetrock | Asphalt shingles, felt paper, sheathing, drip edge, nails, gutters and downspouts | asphalt shingles | 1276 | SF | NEED | 12000 |  |  | No Crew | 0 | 2005 | H | RR-T2 | Requested |  |  | COMPLETE | na |  | Roof leaking for over a year. | 2005-01-14 | JDR | NO CHANGE
2. MA | 1. NYNJTC | 81346 | 384591 | 895260 | 711342 | 62416 |  |  | Legislative | BU | Dutchess-Putnam | Nuclear Lake | Well does not meet Clean Water Act standards |  | Install new well | Contract service to abandon two existing wells and drill new well and connect service to house | Well | 1 | EA | NEED | 10000 |  |  | No Crew | 0 | 2005 | H | RR-T2 | Requested |  |  | COMPLETE |  |  |  | 2005-01-14 | JDR | NO CHANGE
2. MA | 1. NYNJTC | 95355 |  | n/a |  | 77835 |  |  | Legislative | S | Dutchess-Putnam | RPH Cabin (272-23) | Water system does meet requirements of the Safe Drinking Water Act. |  | Replace water pump, extend well casing and back fill concrete block pump house. | Contract services. | Handpump | 1 | EA | NEED | 8000 |  |  | No Crew | 0 | 2005 | H | RR-OS | Requested |  |  | COMPLETE | 0 | 272-23 |  | 2006-02-02 | JDR | COMPLETE
2. MA | 1. NYNJTC | 77139 | 297432 | 822568 |  | 108312 | A |  | Capital | T | Dutchess-Putnam | Bear Mountain (278-279) | [8 empty] | 25000 |  |  | SCA | 12 | 2006 | M | PLC | Requested |  |  | COMPLETE |  |  | Was Pawlings, used at Bear Mountian | 2006-11-12 | RSR | CHANGE DESCRIPTION
2. MA | 1. NYNJTC | 81501 |  | 896024 |  | NEED |  | 2375 |  | OA | Dutchess-Putnam | I-84 overlook (271-22) | Natural succession is taking over the open meadow. |  | Mow field to maintain meadow. | contract mower/ SUP Holder Charlie Dennis to mow approximately 20 acres | Brush mowing, tractor w/rotary mower | 20 | AC | 4880 | 1200 |  |  | No Crew | 0 | 2006 | H | CM | NEED |  |  | COMPLETE | 1000 | 271-22 | Cyclic, was done in 2006 | 2006-11-12 | RSR | COMPLETE
2. MA | 1. NYNJTC | 77139 |  | 898456 | [5 empty] | T | Dutchess-Putnam | Various | Deteriorating trailhead B-boards |  | Replace deteriorated trailhead sign boards | Roof - cedar shakes 8' x 3', 2 12 foot logs 6-8 inches in diameter | Build/AddBulletin Board -each | 6 | EA | 5709.78 | 5000 |  |  | No Crew | 0 | 2006 | H |  |  |  |  | COMPLETE | 2400 |  | 3 built by Boy Scouts and 3 by DPATMC volunteers - 6 now installed, need populating with information & covers installed; local funding | 2006-11-12 | RSR | COMPLETE
2. MA | 1. NYNJTC | 81501 |  | 898455 | [5 empty] | OA | Dutchess-Putnam | Route 52 | Open area subject to succession |  | Mow field every 2-3 years |  | Brush mowing, tractor w/rotary mower | 20 | AC | 4880 | 1200 |  |  | No Crew | 0 | 2006 | H | CM |  |  |  | COMPLETE | 1000 |  | Done in 2006 | 2008-04-09 | JPH | Project Status, Comments
2. MA | 1. NYNJTC | 77139 |  | n/a |  | NEED |  |  |  | WS | Dutchess-Putnam | Messerschmidt | Need monthly testing of total coliform |  | test water systems for TC monthly | Contract services | Water Samples | 12 | EA | NEED | 600 |  |  | No Crew | 0 | 2007 | H | Base | NEED |  |  | COMPLETE | 300 |  | Done by volunteers | 2009-02-16 | JPH | COMPLETE
2. MA | 1. NYNJTC | 101907 |  | 896048 |  | NEED |  |  |  | WS | Dutchess-Putnam | Wiley | Need monthly testing of total coliform |  | test water systems for TC monthly | Contract services | Water Samples | 12 | EA | NEED | 600 |  |  | No Crew | 0 | 2007 | H | Base | NEED |  |  | COMPLETE | 300 |  | Done by volunteers | 2009-02-16 | JPH | COMPLETE
2. MA | 1. NYNJTC | 101908 |  | 896050 |  | NEED |  |  |  | WS | Dutchess-Putnam | Morgan Stewart | Need monthly testing of total coliform |  | test water systems for TC monthly | Contract services | Water Samples | 12 | EA | NEED | 600 |  |  | No Crew | 0 | 2007 | H | Base | NEED |  |  | COMPLETE | 300 |  | Done by volunteers | 2009-02-16 | JPH | COMPLETE
2. MA | 1. NYNJTC | 101909 |  | 86055 |  | NEED |  |  |  | WS | Dutchess-Putnam | RPH Cabin | Need monthly testing of total coliform |  | test water systems for TC monthly | Contract services | Water Samples | 12 | EA | NEED | 600 |  |  | No Crew | 0 | 2007 | H | Base | NEED |  |  | COMPLETE | 300 |  | Done by volunteers | 2009-02-16 | JPH | COMPLETE
2. MA | 1. NYNJTC | 95200 |  | 898465 | 712630 | 77843 | A |  | DM | S | Dutchess-Putnam | Depot Hill Road/Morgan Stewart Shelter | Roof is nearing the end of its life span. |  | Install new asphalt shingles | rolled roofing, roofing nails, drip edge, plywood sheathing | Rolled Roofing | 10 | SQ | 1004.5 | 1004.5 |  |  | No Crew | 0 | 2007 | M | RR-OS | Requested |  |  | COMPLETE | 1000 |  |  | 2008-04-09 | JPH | Project Status
2. MA | 1. NYNJTC | 77139 | 384797 | 896068 |  | NEED |  |  |  | B | Dutchess-Putnam | Old Rt. 55 (Whaley Lake Stream) | Deteriorating Bridge |  | Replace Bridge |  |  |  |  | NEED | 3000 |  |  |  |  | 2007 | H | RR-T | NEED |  |  | COMPLETE | 3000 |  | Accelerate funding; needs project review | 2008-04-09 | JPH | Project Status
2. MA | 1. NYNJTC |  |  |  |  | NEED |  |  |  | T | Dutchess-Putnam | Chapman Road | Wet, eroded trail |  | Puncheon | Plastic posts and planking | Build/Add puncheon | 100 | LF |  | 4750 |  |  | Mid-Atlantic | 1 | 2007 | M | RR-T | NEED |  |  | COMPLETE |  |  | Done 9/07 | 2008-04-09 | JPH | Project Status, Comments
2. MA | 1. NYNJTC |  |  |  |  | NEED |  |  |  | S | Dutchess-Putnam | Telephone Pioneers Shelter | Roof is nearing the end of its life span |  | Install new wood as needed, asphalt shingles, & drip edge | rolled roofing, roofing nails, drip edge, plywood sheathing | Rolled roofing | 10 | SQ |  |  |  |  | No Crew | 0 | 2007 | M | RR-OS | NEED |  |  | COMPLETE | 1000 |  | Morgan Stewart roof done 2006--donated shingles | 2008-04-09 | JPH | Project Status
2. MA | 1. NYNJTC | 81346 |  | 836499 |  | 119475 |  |  | DM | BU | Dutchess-Putnam | Nuclear Lake | Inadequate access road and deteriorating caretaker house |  |  | Contract |  | 1 | EA | 252023.09 | 252023.09 |  |  | No Crew | 0 | 2008 | H | Dam Safety | FUNDED |  |  | COMPLETE |  |  | To be completed with BOR Agreement | 2009-02-16 | JPH | COMPLETE
2. MA | 1. NYNJTC |  |  |  |  | NEED |  |  |  | B | Dutchess-Putnam | Yegella Farm (268-38) | Deteriorating stiles and bridge |  | Replace stiles and bridge | [10 empty] | 2008 | H |  | NEED |  |  | COMPLETE | 400 |  | Likely local funding | 2009-02-16 | JPH | COMPLETE
2. MA | 1. NYNJTC |  |  |  |  | NEED |  |  |  | WS | Dutchess-Putnam | Messerschmidt | Need monthly testing of total coliform |  | test water systems for TC monthly | Contract services | Water Samples | 12 | EA | NEED | 600 |  |  | No Crew | 0 | 2008 | H | Base | NEED |  |  | COMPLETE | 300 |  |  | 2009-02-16 | JPH | COMPLETE
2. MA | 1. NYNJTC |  |  |  |  | NEED |  |  |  | WS | Dutchess-Putnam | Wiley | Need monthly testing of total coliform |  | test water systems for TC monthly | Contract services | Water Samples | 12 | EA | NEED | 600 |  |  | No Crew | 0 | 2008 | H | Base | NEED |  |  | COMPLETE | 300 |  |  | 2009-02-16 | JPH | COMPLETE
2. MA | 1. NYNJTC |  |  |  |  | NEED |  |  |  | WS | Dutchess-Putnam | Morgan Stewart | Need monthly testing of total coliform |  | test water systems for TC monthly | Contract services | Water Samples | 12 | EA | NEED | 600 |  |  | No Crew | 0 | 2008 | H | Base | NEED |  |  | COMPLETE | 300 |  |  | 2009-02-16 | JPH | COMPLETE
2. MA | 1. NYNJTC |  |  |  |  | NEED |  |  |  | WS | Dutchess-Putnam | RPH Cabin | Need monthly testing of total coliform |  | test water systems for TC monthly | Contract services | Water Samples | 12 | EA | NEED | 600 |  |  | No Crew | 0 | 2008 | H | Base | NEED |  |  | COMPLETE | 300 |  |  | 2009-02-16 | JPH | COMPLETE
2. MA | 1. NYNJTC |  |  |  |  | NEED |  |  |  | T | Dutchess-Putnam | Trail south of Penny Rd. to Nuclear Lake boundary (269-01) | Rotting puncheon over beaver swamp |  | Replace puncheon and substructure | Plastic posts and planking |  | 75 | LF | [6 empty] | 2008 | H |  | NEED |  |  | COMPLETE | 600 |  |  | 2009-02-16 | JPH | COMPLETE
2. MA | 1. NYNJTC |  |  |  |  | NEED |  |  |  | P | Dutchess-Putnam | Wiley & Telephone Pioneer Privies | Long term problem with finding appropriate location for privy hole |  | Convert to moldering privies | Wood and hardware cloth (match materials list used for Morgan Stewart privy) | [7 empty] | No Crew | 0 | 2008 | M |  | NEED |  |  | COMPLETE | 600 |  |  | 2009-02-16 | JPH | COMPLETE
2. MA | 1. NYNJTC | 81346 |  | 836483 |  | 126223 | A |  | DM | BU | Dutchess-Putnam | Nuclear Lake | potholes in access rd |  | repair holes in access rd | Dump truck full of stone, equipment to spread it around. One truckload of 2-3" stone should be sufficient. 20 tons (1.4 tons per CY) | Borrow, spread w/dozer, crushed stone, 1/2" |  | CY |  | 56140.18 |  |  | No Crew | 0 | 2008 | H | RR-S | Requested |  |  | COMPLETE |  |  | May hamper emergency vehicles | 2009-03-17 | JDR | Remove PMIS Request
2. MA | 1. NYNJTC | 77139 | 297432 | 712363 | 711324 | 117913 | A | 2040 | Capital | B | Dutchess-Putnam | RPH Cabin | Bridge is subject to washout |  | replace or rebuild existing bridge | lumber, hardware | Build/AddLog Bridge -sf | 60 | SF | 4920 | 4920 |  |  | Mid-Atlantic | 1 | 2008 | M | RR-T | Requested |  |  | COMPLETE | 1500 |  | Done 7/07 | 2008-04-09 | JPH | Project Status, Comments
2. MA | 1. NYNJTC |  |  |  |  | NEED |  | 2040 |  | T | Dutchess-Putnam | Swamp at Sweetman | Wet, eroded trail |  | Puncheon | Plastic posts and planking | Build/Add puncheon | 100 | LF |  | 4750 |  |  | Mid-Atlantic | 1 | 2008 | M | RR-T | Not Requested |  |  | COMPLETE |  |  | Done 7/07 | 2008-04-09 | JPH | Project Status, Comments
2. MA | 1. NYNJTC |  |  |  |  | NEED |  |  |  | T | Dutchess-Putnam | Old Route 55 to Whaley Lake stream bridge (269-14) | Boggy wet area |  | Build puncheon | Plastic posts and planking |  | 300 | LF |  |  |  |  | SCA | 1 | 2008 | M | PLC | NEED |  |  | COMPLETE | 2400 |  | Done 10/07 | 2008-04-09 | JPH | Project Status, Comments
2. MA | 1. NYNJTC | 101909 |  |  |  | NEED |  |  | RM | WS | Dutchess-Putnam | RPH Cabin | Need monthly testing of total coliform |  | test water systems for TC monthly | Contract services | Water Samples | 12 | EA | NEED | 600 | 485.2798 | 114.7202 | No Crew | 0 | 2009 | H | none | n/a | ATPO | CE | COMPLETE | 300 |  | Volunteers plan to continue to do | 2010-01-14 | JPH
2. MA | 1. NYNJTC | 101908 |  |  |  | NEED |  |  | RM | WS | Dutchess-Putnam | Morgan Stewart | Need monthly testing of total coliform |  | test water systems for TC monthly | Contract services | Water Samples | 12 | EA | NEED | 600 | 485.2798 | 114.7202 | No Crew | 0 | 2009 | H | none | n/a | ATPO | CE | COMPLETE | 300 |  | Volunteers plan to continue to do | 2010-01-14 | JPH
2. MA | 1. NYNJTC | 101907 |  |  |  | NEED |  |  | RM | WS | Dutchess-Putnam | Wiley | Need monthly testing of total coliform |  | test water systems for TC monthly | Contract services | Water Samples | 12 | EA | NEED | 600 | 485.2798 | 114.7202 | No Crew | 0 | 2009 | H | none | n/a | ATPO | CE | COMPLETE | 300 |  | Volunteers plan to continue to do | 2010-01-14 | JPH
2. MA | 1. NYNJTC | NEED |  |  |  | NEED |  |  | RM | WS | Dutchess-Putnam | Messerschmidt | Need monthly testing of total coliform |  | test water systems for TC monthly | Contract services | Water Samples | 12 | EA | NEED | 600 | 485.2798 | 114.7202 | No Crew | 0 | 2009 | H | none | n/a | ATPO |  | COMPLETE | 300 |  | Volunteers plan to continue to do | 2010-01-14 | JPH
2. MA | 1. NYNJTC |  |  |  |  | NEED |  |  | RM | OA | Dutchess-Putnam | I-84 overlook (271-22) | Natural succession is taking over the open meadow. |  | Mow field to maintain meadow. | contract mower/ SUP Holder Charlie Dennis to mow approximately 20 acres | Brush mowing, tractor w/rotary mower | 20 | AC | 4880 | 1200 | 970.5597 | 229.4403 | No Crew | 0 | 2009 | H | CM | NEED | ATPO | NA | COMPLETE |  |  | Cyclic, was done in 2006 | 2010-01-14 | JPH | NEW PROJECT
2. MA | 1. NYNJTC | N/A | N/A | N/A | N/A | N/A |  |  |  | ED | Dutchess-Putnam | Dutchess-Putnam | Low neighbor knowledge of AT |  | Publish neighbor brochure | [5 empty] | 1000 | 0 | 0 | No Crew | 0 | 2010 | M |  | Not Requested | n/a |  | COMPLETE | 1000 |  | aprox 15 years ago we had such a brochure. Should be redone to educate corridor neighbors including town officials. 2010 LL Bean grant requested | 2013-06-12 | JCB | Changed to Completed
2. MA | 1. NYNJTC | 77139 | 297432 | 712383 | 1479505 | 126217 | A |  | DM | T | Dutchess-Putnam | Route 22 (Swamp River & Hiller Brook) | Wetland crossing |  | Construct 500 linear feet of raised boardwalk and puncheon through a wetland area near Pawling, New York. It will utilize helical pier technology which has been successfully installed on other sections of the Appalachian Trail and provides for the free-flow of water under the structure reducing impacts on the sensitive wetland area. | Helical piers; 2x10 rough cut oak stringers, 2x8 rough cut planking, spikes | Build/Add Boardwalk | 1600 | LF | NEED | 90000 | 72791.9767 | 17208.0233 | Mid-Atlantic | 5 | 2010 | H | ARRA |  | APPA | 25370 | COMPLETE | 200000 |  | Was pmis# 49983 in 2005 - was 2005, re-estimate costs (DPATMC to get LF figure recalculated), Problem worsening | 2013-02-25 | JCB | Project completed by 12/12/11, and moved to the completed project list
2. MA | 1. NYNJTC | 77139 | 297432 | N/F | N/F | N/F |  |  |  | T | Dutchess-Putnam | TNC Easement Relo | trail relocation |  |  |  | Build/AddTrail: New -lf | 2500 | LF |  |  | 0 | 0 | No Crew | 0 | 2010 |  | n/a |  | APPA | 25372 - need CE | COMPLETE |  |  | Compliance review done June 2009, waiting NPS clearance to proceed | 2013-02-25 | JCB | Project completed by 12/12/11, and moved to the completed project list
2. MA | 1. NYNJTC | 101907 | N/A | N/A | N/A | N/A |  |  | RM | WS | Dutchess-Putnam | Messerschmidt | Need monthly testing of total coliform |  | test water systems for TC monthly | Contract services | Water Samples | 12 | EA | NEED | 300 | 242.6399 | 57.3601 | No Crew | 0 | 2010 | H | Base |  |  |  | COMPLETE | 300 |  |  | 2013-02-25 | JCB | Project completed by 12/12/11, and moved to the completed project list
2. MA | 1. NYNJTC | 101907 | N/A | N/A | N/A | N/A |  |  | RM | WS | Dutchess-Putnam | Wiley | Need monthly testing of total coliform |  | test water systems for TC monthly | Contract services | Water Samples | 12 | EA | NEED | 300 | 242.6399 | 57.3601 | No Crew | 0 | 2010 | H | Base |  |  |  | COMPLETE | 300 |  |  | 2013-02-25 | JCB | Project completed by 12/12/11, and moved to the completed project list
2. MA | 1. NYNJTC | 101908 | N/A | N/A | N/A | N/A |  |  | RM | WS | Dutchess-Putnam | Morgan Stewart | Need monthly testing of total coliform |  | test water systems for TC monthly | Contract services | Water Samples | 12 | EA | NEED | 300 | 242.6399 | 57.3601 | No Crew | 0 | 2010 | H | Base |  |  |  | COMPLETE | 300 |  |  | 2013-02-25 | JCB | Project completed by 12/12/11, and moved to the completed project list
2. MA | 1. NYNJTC | 101909 | N/A | N/A | N/A | N/A |  |  | RM | WS | Dutchess-Putnam | RPH Cabin | Need monthly testing of total coliform |  | test water systems for TC monthly | Contract services | Water Samples | 12 | EA | NEED | 300 | 242.6399 | 57.3601 | No Crew | 0 | 2010 | H | Base |  |  |  | COMPLETE | 300 |  |  | 2013-02-25 | JCB | Project completed by 12/12/11, and moved to the completed project list
2. MA | 1. NYNJTC | 77139 | 297432 | 712384 | 7900458 (PST WO still needs to be closed out) | 179758 | A |  | CI | T | Dutchess-Putnam | Route 22 (Swamp River & Hiller Brook) | Wetland crossing |  | Install puncheon | Helical piers; 2x10 rough cut oak stringers, 2x8 rough cut planking, spikes | Build/Add Boardwalk | 1500 | LF |  | 102600 | #N/A | #N/A | Mid-Atlantic | 5 | 2010 | H | RR-S |  |  |  | COMPLETE | 200000 |  | 2008 R/R Demo Funds | 2013-02-25 | JCB | Project completed by 12/12/11, and moved to the completed project list
2. MA | 1. NYNJTC | 101907 | N/A | N/A | N/A | N/A |  |  | RM | WS | Dutchess-Putnam | Wiley | Need monthly testing of total coliform |  | test water systems for TC monthly | Contract services | Water Samples | 12 | EA | NEED | 600 | 485.2798 | 114.7202 | No Crew | 0 | 2011 | H | Base | NEED |  |  | COMPLETE | 300 |  | Pump broken | 2013-06-12 | JCB | Changed to Completed
2. MA | 1. NYNJTC | 77139 | 297432 | 712384 | 711324 (PST WO still needs to be closed out) | 117913 | A | 2040 | CI | B | Dutchess-Putnam | Route 22 (Swamp River & Hiller Brook) | Deteriorating bridge- rapidly getting worse. Cribbing all rotted |  | replace bridge | lumber, hardware | Build/AddLog Bridge -sf | 80 | SF | 6560 | 6560 | #N/A | #N/A | Mid-Atlantic | 1 | 2011 | H | RR-T |  |  |  | COMPLETE | 3000 |  | link to boardwalk project Condition much degraded. | 2013-02-25 | JCB | Project was 80% completed by 12/12/11, and moved to the completed project list
2. MA | 1. NYNJTC | 77139 | 297432 | 712384 | 7900458 (PST WO still needs to be closed out) | 179758 | A |  |  | T | Dutchess-Putnam | Route 22 (Swamp River & Hiller Brook) | Continue boardwalk Project |  |  | 34,500 steel piers, 6,800 lumber, fasteners, 8,000 crew, 4,500 ATC staff (ft), 10,765 ATC OH @ 20% |  |  |  |  | 65000 |  |  | Mid-Atlantic |  | 2011 | H |  |  | APPA |  | COMPLETE | 65000 |  | see BS e-mail 12/10/10 | 2013-02-25 | JCB | Project was 95% completed by 12/12/11, and moved to the completed project list
2. MA | 1. NYNJTC | 101907 | N/A | N/A | N/A | N/A |  |  | RM | WS | Dutchess-Putnam | Messerschmidt | Need monthly testing of total coliform |  | test water systems for TC monthly | Contract services | Water Samples | 12 | EA | NEED | 600 | 485.2798 | 114.7202 | No Crew | 0 | 2011 | H | Base |  |  |  | COMPLETE | 300 |  |  | 2013-02-25 | JCB | Project completed by 12/12/11, and moved to the completed project list
2. MA | 1. NYNJTC | 101908 | N/A | N/A | N/A | N/A |  |  | RM | WS | Dutchess-Putnam | Morgan Stewart | Need monthly testing of total coliform |  | test water systems for TC monthly | Contract services | Water Samples | 12 | EA | NEED | 600 | 485.2798 | 114.7202 | No Crew | 0 | 2011 | H | Base |  |  |  | COMPLETE | 300 |  |  | 2013-02-25 | JCB | Project completed by 12/12/11, and moved to the completed project list
2. MA | 1. NYNJTC | 101909 | N/A | N/A | N/A | N/A |  |  | RM | WS | Dutchess-Putnam | RPH Cabin | Need monthly testing of total coliform |  | test water systems for TC monthly | Contract services | Water Samples | 12 | EA | NEED | 600 | 485.2798 | 114.7202 | No Crew | 0 | 2011 | H | Base |  |  |  | COMPLETE | 300 |  |  | 2013-02-25 | JCB | Project completed by 12/12/11, and moved to the completed project list
2. MA | 1. NYNJTC | 88969 | N/A | N/A | N/F | N/F |  |  | CI | BU | Dutchess-Putnam | Nuclear Lake Garage (269-18) | Decaying walls (roof believed already done) |  | Repair or replace | [6 empty] | 0 | 0 |  |  | 2011 | H |  | NEED |  |  | UNKNOWN | 8000 |  | Deteriorating - need by 2011: used also for Nuclear Lake dam maintenance equipment | 2013-10-22 | JCB | Changed status to UKNOWN; Moved to Completed Tab
2. MA | 1. NYNJTC | 95589, 95591, 95590 | N/A | N/F | 7897270 | N/F |  |  | DM | P | Dutchess-Putnam | Wiley, Morgan Stewart & Telephone Pioneer Privies | Privy roof(s) nearing end of life span, privy bodies aging (approx. 20 years old) |  | Install new asphalt shingles, rehab as needed | New wood frame privy upper portion as needed | Structure | 3 | EA |  |  | 0 | 0 | No Crew | 0 | 2011 | M | RR-OS | NEED |  |  | UNKNOWN | 2000 |  | Telephone privy done | 2013-10-22 | JCB | Changed status to UKNOWN; Moved to Completed Tab
2. MA | 1. NYNJTC | 81501 | 375124 | [5 empty] | RM | OA | Dutchess-Putnam | I-84 overlook (271-22) | Natural succession is taking over the open meadow. |  | Mow field to maintain meadow. | contract mower/ SUP Holder Charlie Dennis to mow approximately 20 acres | Brush mowing, tractor w/rotary mower | 20 | AC | 4880 | 1200 | 970.5597 | 229.4403 | No Crew | 0 | 2012 | H | CM | NEED |  |  | COMPLETE |  |  | Cyclic, was done in 2006 and 2009 ($800) | 2013-10-20 | JCB | Changed to COMPLETE
2. MA | 1. NYNJTC | 101907 | N/A | N/A | N/A | N/A |  |  | RM | WS | Dutchess-Putnam | Wiley | Need monthly testing of total coliform |  | test water systems for TC monthly | Contract services | Water Samples | 12 | EA | NEED | 600 | 485.2798 | 114.7202 | No Crew | 0 | 2012 | H | Base | NEED |  |  | COMPLETE | 300 |  | Pump broken | 2013-06-12 | JCB | Changed to Completed
2. MA | 1. NYNJTC | 101907 | N/A | N/A | N/A | N/A |  |  | RM | WS | Dutchess-Putnam | Messerschmidt | Need monthly testing of total coliform |  | test water systems for TC monthly | Contract services | Water Samples | 12 | EA | NEED | 600 | 485.2798 | 114.7202 | No Crew | 0 | 2012 | H | Base |  |  |  | COMPLETE | 300 |  |  | 2013-02-25 | JCB | Project completed by 12/12/11, and moved to the completed project list
2. MA | 1. NYNJTC | 101908 | N/A | N/A | N/A | N/A |  |  | RM | WS | Dutchess-Putnam | Morgan Stewart | Need monthly testing of total coliform |  | test water systems for TC monthly | Contract services | Water Samples | 12 | EA | NEED | 600 | #N/A | #N/A | No Crew | 0 | 2012 | H | Base |  |  |  | COMPLETE | 300 |  |  | 2013-02-25 | JCB | Project completed by 12/12/11, and moved to the completed project list
2. MA | 1. NYNJTC | 101909 | N/A | N/A | N/A | N/A |  |  | RM | WS | Dutchess-Putnam | RPH Cabin | Need monthly testing of total coliform |  | test water systems for TC monthly | Contract services | Water Samples | 12 | EA | NEED | 600 | #N/A | #N/A | No Crew | 0 | 2012 | H | Base |  |  |  | COMPLETE | 300 |  |  | 2013-02-25 | JCB | Project completed by 12/12/11, and moved to the completed project list
2. MA | 1. NYNJTC | 77139 | 297432 | 5108709, 5109026 | 5109578 (PST WO may still need to be closed out) | 164064A |  |  | CI | T | Dutchess-Putnam | Route 22 (Swamp River & Hiller Brook) | Phase 2 include bridge |  |  |  | Build/Add: Boardwalk |  | LF |  | 86658 |  |  |  |  | 2012 | H | RR-S | FUNDED - 2012 | APPA |  | COMPLETE | 60000 |  |  | 2009-06-29 | JDR | ADD Project
2. MA | 1. NYNJTC | 95198 | N/A | N/F | N/F | N/F |  |  | DM | S | Dutchess-Putnam | Wiley Shelter | Roof and floor reaching end of lifespan |  | Install new roof and flooring | rolled roofing, roofing nails, drip edge, plywood sheathing, flooring | Rolled roofing | 1 | SQ |  |  | 0 | 0 | No Crew | 0 | 2012 | M | RR-OS | NEED |  |  | UNKNOWN | 2000 |  |  | 2013-10-22 | JCB | Changed status to UKNOWN; Moved to Completed Tab
2. MA | 1. NYNJTC | 77139 | N/F | N/F | N/F | N/F |  |  |  |  | Dutchess-Putnam | N of Duell Hollow Brook | Trail too close to boundary |  | Relocation |  | Build/AddTrail: New -lf | 200 | LF |  |  |  |  | No Crew |  | 2012 | H |  |  | APPA |  | UNKNOWN |  | 267-10 |  | 2013-10-22 | JCB | Changed status to UKNOWN; Moved to Completed Tab
2. MA | 1. NYNJTC | 77139 | N/F | N/F | N/F | N/F |  |  |  |  | Dutchess-Putnam | S. of Rt. 52 | Trail too close to boundary |  | Relocation |  | Build/AddTrail: New -lf | 200 | LF |  |  |  |  | No Crew |  | 2012 | H |  |  | APPA |  | UNKNOWN |  | 271-08 |  | 2013-10-22 | JCB | Changed status to UKNOWN; Moved to Completed Tab

## Instruction_Sheet
2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020
PAST YEAR(s) (requested in 2010) | CURRENT YEAR (requested in 2011) | OUT | Five Year Plan |  |  |  | NEW
|  | YEAR | (requested
|  | (requested in 2012) | in 2013)
Update Project Status | Confirm Projects | Review Projects | Review and Update | Adjust Project Scopes | Re-Arrange Projects | Remove Completed Projects | Add new Projects
Capital Planning
Five Steps: Fall 2013
The Capital Plan is designed to capture all of the A.T. project needs that may require National Park Service funding or projects that will take place on National Park Service lands and require environmental compliance.
1. Review past year projects (2013 and earlier) and indicate which ones have been completed, which ones need to be moved to another year because they were not done, or which ones can be removed from the list altogether. Once updated, the Plan should only contain projects for 2014 and beyond.
2. Review current year (2014) and next year (2015) projects to confirm scheduled work. Changes to the plan should be brought to the attention of the ATC regional staff as soon as possible so adjustments may be considered. No additional funding is available in these years. Any new or emergency project will need to replace or substitute an existing project on the list.
3. Review all other projects (2016 – 2019) on the list and make any necessary changes. When making changes, consider both the year planned and the scope of work.
4. Add new projects to 2020. 2020 is the only year for which new funding may be available; new projects should be listed here.
5. For each project, please indicate who the land owner is. It is particularly important to note any project that is wholly or partially located on NPS-APPA lands to aid in scheduling compliance reviews.
Use “Enviro Compliance Lead Agency” column to specify land/agency ownership.
6. Indicate the "AT ID" for each project, which is found in Google Earth. This is neccessary to link Capital Plan projects to deficiencies identified during the Trail Assessment. This will also improve reporting of project completion.