## Project_List
Region | CLUB | FMSS Location Number | FMSS Asset # | FMSS WO # | PST WO# | PMIS # | Component | ATC Project # | WORK TYPE | ASSET TYPE | DISTRICT | LOCATION | DEFICIENCY | Trail Assessment "AT ID" (indicate ID number, or range of IDs, project will address) | PROJECT DESCRIPTION | LIST ADDITIONAL MATERIALS AND/OR SERVICES NEEDED | ITEM | QTY | U.O.M | NPS Estimate | NPS Request Amount | ATC Direct Project | ATC Indirect (23.64%) | CREW | CREW WEEKS | YEAR | CLUB PRIORITY | FUND TYPE | NPS FUNDING Status | ENVIRO COMPLIANCE LEAD AGENCY? | PEPC # | PROJECT STATUS | CLUB ESTIMATE | Seg./Tract # | COMMENTS/OTHER: | LAST UPDATED | UPDATED BY: | CHANGES
2. MA | 1. NYNJTC | N/A | N/A | N/A | N/A | N/A |  |  |  | NR | New Jersey | Various | Exotic plant species competing with NHS |  | Control exotic invasive plants |  | contractor | 32 | hours | 1300 | 0 | 0 | 0 | No Crew | 0 | 2015 | M | NR | Not Requested |  |  | UNKNOWN |  |  | Contract with Ted Elliman. Ask Kent for details on sites, etc. | 2009-03-10 | BS
2. MA | 1. NYNJTC | 101906 | N/F | 896034 | 711321 | 77844 | A |  | CI | PL | NJ, NY/NJ line - Liberty Crn Rd | Pochuck Wetland (304) | Need accessible parking area to accommodate visitors to newly constructed accessible 2-mile-long boardwalk. |  | Build accessible parking lot. | Contract services for design and construction. | Base Course, crushed 3/4" stone base, compacted, 6" deep | 3500 | SF | 14315 | 44315 | 35841.9605 | 8473.0395 | No Crew | 0 | 2013 | H | RR-T | Requested | NJ |  | In Progress | 5000 | 304 | Accessible parking for 7 cars and two buses | 2013-02-25 | JCB | As of 12/12/11, was listed as in planning. WAS 2012; MOVED to 2013
2. MA | 1. NYNJTC | 72470 | N/F | NEED | 5104593 | 164045 | A |  | DM | T | NJ, NY/NJ line - Liberty Crn Rd | Pochuck (304) | Boardwalk aging - constructed 1999-2002 |  | Replace 1500 lf aging decking |  |  |  |  | 4750 | 4750 | 3841.7988 | 908.2012 | Mid-Atlantic | 1 | 2013 | M | RR-T | FUNDED - 2013 |  |  | NEW PROJECT |  |  |  | 2012-10-01 | JDR | FUNDED
2. MA | 1. NYNJTC | 77147 | 297367 | 9310808 | 9311501 | 190255 | A |  | DM | T | NJ, NY/NJ line - Liberty Crn Rd | Pochuck (304) | Boardwalk aging - constructed 1999-2002 |  | Replace 1500 lf aging decking |  |  | 1500 | LF |  | 9800 | 7926.2375 | 1873.7625 | Mid-Atlantic | 2 | 2014 | M | RR-T | Requested |  |  | REQUESTED |  |  |  | 2012-01-24 | JDR | Requested
2. MA | 1. NYNJTC | 105968 | N/F | 9306814 | 9306920 | 189386 | A |  | CI | PL | NJ, NY/NJ line - Liberty Crn Rd | Rt 94 (303-01,08) | Parking area too small to accommodate use. |  | Increase size of parking area to accommodate 20 cars. | Contract design and construction services. Need 35 cubic yards of gravel. | Base Course, crushed 3/4" stone base, compacted, 6" deep | 3000 | SF | 12270 | 10000 | 8087.9974 | 1912.0026 | No Crew | 0 | 2015 | M | CM | Requested | State |  |  | 2000 | 303-01 08 | On state land | 2012-01-20 | JDR | Requested
2. MA | 1. NYNJTC | 72470 | N/F | N/F | N/F | N/F |  |  | DM | T | NJ, NY/NJ line - Liberty Crn Rd | Pochuck (304) | Boardwalk aging - constructed 1999-2002 |  | Replace 1500 lf aging decking |  | Repair Boardwalk | 1500 | LF |  | 9500 | 7683.5975 | 1816.4025 | Mid-Atlantic | 1 | 2016 | M | RR | FUNDED - 2012 |  |  | FUNDED - 2012 |  |  |  | 2013-02-25 | JCB | WAS 2012 MOVED to 2016. Club stated not in 2012 budget
2. MA | 1. NYNJTC | 77147 | 297367 | 9320615 | 9323535 | 191064 |  |  | DM | T | NJ, NY/NJ line - Liberty Crn Rd | Pochuck (304) | Boardwalk aging - constructed 1999-2002 |  | Replace 1500 lf aging decking |  |  | 1500 | LF |  | 9750 | 7885.7975 | 1864.2025 | Mid-Atlantic | 1 | 2016 | M | RR-T | Requested |  |  | NEW PROJECT |  |  | Was 2015 - move to 2016 | 2012-01-26 | JDR | REQUESTED
2. MA | 1. NYNJTC | 105972 | N/F | 9306962 | 9306975 | 189394 | A |  | CI | PL | NJ, NY/NJ line - Liberty Crn Rd | Warwick turnpike (302-07) | Parking area too small to accommodate use. |  | Increase size of parking area to accommodate 10 cars. | Contract design and construction services. Need 17 cubic yards of gravel. | Base Course, crushed 3/4" stone base, compacted, 6" deep | 1500 | SF | 6135 | 6000 | 4852.7984 | 1147.2016 | No Crew | 0 | 2016 | M | CM | Requested |  |  |  | 1000 | 302-07 | Local land use regs (Highlands Act) may impede improving parking? | 2012-01-20 | JDR | Requested
2. MA | 1. NYNJTC | 77150 | 297369 | 712371 | 711329 | 117915 | A |  | CI | T | NJ, Oil City Rd - Brink Rd Shelter | Wallkill River (306) | Trail is co-aligned with road and not in optimal location. |  | Construct 2000 feet of boardwalk to cross Wallkill River bridge. | Helical piers | Build/AddBoardwalk -lf | 2000 | LF | 64740 | 40000 | 32351.9896 | 7648.0104 | Mid-Atlantic | 8 | 2013 | H | RR-T | Requested |  |  |  | na | 306 | These figures taken from NPS Trail Costs seem wacky (too high) Based on 2009 helical pier costs for Swamp River, NPS Request Amount is way to LOW | 2013-02-25 | JCB | CHANGED from 4 crew weeks and 2011 to 8 crew weeks and 2013
2. MA | 1. NYNJTC | 77150 | 297369 | N/F | N/F | 60054 | A |  | DM | Dam | NJ, Oil City Rd - Brink Rd Shelter | Banks Pond (305) | Low-hazard dam seriously deficient. |  | Maintain it or drain it. | Contract services. |  |  |  | NEED | 10000 | 8087.9974 | 1912.0026 | No Crew | 0 | 2013 | L | CM |  |  |  | UNKNOWN | ? | 305 | Ask Bob Gray. Need improvements to dam access road to accomplish repairs, which may exceed cost of dam repair. | 2013-02-25 | JCB | WAS 2012 MOVED to 2013 MOVED to 2010
2. MA | 1. NYNJTC | 77150 | 297369 | 9310823 | 9311501 | 190255 |  |  | CI | T | NJ, Oil City Rd - Brink Rd Shelter | Kitaninny Ridge Rt 206 (312) | Footpath follows old road bed which is poorly designed, too steep and badly eroded. |  | Relocate/reconstruct 1/2 mile section of footpath. |  | Build/AddTrail: New -lf | 1000 | LF | 7650 | 4900 | 3963.1187 | 936.8813 | Mid-Atlantic | 1 | 2014 | H | RR-T | Requested |  |  | REQUESTED | 3000 | 312 |  | 2012-01-24 | JDR | Requested
2. MA | 1. NYNJTC | 77150 | 297369 | N/F | N/F | N/F |  |  | CI | T | NJ, Oil City Rd - Brink Rd Shelter | Surprise Lake (301-01) | Illegal ATV use on A.T. lands. |  | Install boulder and gate closures. | Contract services. | Build/Add: Gate-each | 2 | EA | 2893.8 | 2893.8 | 2340.5047 | 553.2953 | No Crew | 0 | 2015 | H | CM |  |  |  | UNKNOWN | 2000 | 301-01 |  | 2009-03-10 | BS
2. MA | 1. NYNJTC | 77150 | 297369 | N/F | N/F | N/F |  |  | CI | T | NJ, Oil City Rd - Brink Rd Shelter | Banks Pond (305) | Illegal ATV use on A.T. lands. |  | Install boulder and gate closures. | Twenty 2-ton boulders. | Build/Add: Gate-each | 4 | EA | 5787.6 | 5787.6 | 4681.0094 | 1106.5906 | No Crew | 0 | 2015 | M | CM |  |  |  | UNKNOWN | 5000 | 305 |  | 2009-03-10 | BS
2. MA | 1. NYNJTC | 77150 | 297369 | 712370 | 711321, 9318751 | 190640 |  |  | DM | T | NJ, Oil City Rd - Brink Rd Shelter | Vernie Swamp | puncheon does not extend far enough and existing puncheon is deteriorated |  | Extend length of existing puncheon and replace old material |  | Build/AddPuncheon -lf | 2000 | LF | 18240 | 18240 | #REF! | #REF! | Mid-Atlantic | 3 | 2015 | M | RR-T | Requested |  |  |  | 13680 |  | This figure is based on A.T Trail costs. | 2012-01-25 | JDR | REQUESTED (Was 2007 MOVE to 2015)
2. MA | 1. NYNJTC | 102009 | N/F | 898445 | 712630 | 77843 | A |  | CI | C | NJ, Oil City Rd - Brink Rd Shelter | Brinks Shelter | Inadequate facility, poor location |  | Replace shelter with tent pads | Fine grade, fine grade for slab on grade, hand grading,Clearing brush with saw, by hand, includes cutting and site cleanup, backfill, light soil by hand, no compaction | Tent Pad | 10 | EA | 1641.4 | 1641.4 | 14752.5073 | #REF! | No Crew | 0 | 2015 | L | RR-OS | Requested |  |  | Awaiting Funding |  |  | Surrounding area apparently rattlesnake habitat, making relocation of shelter difficult, location still poor | 2013-02-25 | JCB | Club stated that the project was "in limbo" due to the risks of relocating the shelter.
2. MA | 1. NYNJTC | 95269 | 281724 | 898446 | 712630 | 190640 |  |  | CI | S | NJ, Oil City Rd - Brink Rd Shelter | Gren Anderson shelter (311) | Inadequate facility, poor location |  | Relocate and replace shelter |  | Log Shelter | 200 | SF | 18608 | 18608 | 1327.5639 | -13111.1073 | Mid-Atlantic | 2 | 2015 | M | RR-T | Requested |  |  | Awaiting Funding | na | 311 | Moldering privy installed 2011, consider minor relo of shelter when needs rebuilding | 2013-02-25 | JCB | Club comments added
2. MA | 1. NYNJTC | 77150 | 297369 | 898451 | N/F | N/F |  |  | CI | CR | NJ, Oil City Rd - Brink Rd Shelter | Off Crigger Road (310-01) | No control of vehicular access. |  | Install gate. | Contract construction/installation services. Materials: 12 foot steel pipe gate and posts, 2 cubic yards of concrete, Best lock. | Build/Add: Gate-each | 1 | EA | 1446.9 | 1446.9 | 15050.1456 | 17280.4361 | No Crew | 0 | 2015 | L | CM | NEED |  |  | UNKNOWN | 1000 | 310-01 | State Land | 2009-03-10 | BS | Move to 2015
2. MA | 1. NYNJTC | 95215 | N/A | 898448 | 712634 | 117927 | A |  | CI | S | NJ, Oil City Rd - Brink Rd Shelter | Rutherford Shelter | Shelter old and inadequate to accommodate demand |  | Replace shelter |  | Log Shelter | 200 | SF | 18608 | 18608 | 15050.1456 | 3557.8544 | Mid-Atlantic | 2 | 2018 | M | RR-OS | NOT FUNDED | [6 empty] | 2013-02-25 | JCB | WAS 2010 MOVED to 2018
2. MA | 1. NYNJTC | 105299 | N/F | 898447 | N/F | 126219 | A |  | CI | B | NJ, Oil City Rd - Brink Rd Shelter | Wallkill River (306) | Trail is co-aligned with road and not in optimal location. |  | Construct 150-foot-long bridge | Contract design and construction services. | Build/AddLog Bridge -sf | 600 | SF | 49200 | 116100 | 93901.65 | 22198.35 | Mid-Atlantic | 4 | 2018 | H | RR-S | Requested |  |  |  | 500000 | 306 | These figures taken from NPS Trail Costs seem wacky (too low $82/sq ft.) | 2010-07-23 | JDR | PLACEHOLDER
2. MA | 1. NYNJTC | 77154 | 297371 | 893319 | 9311501 | 190255 |  |  | DM | T | NJ, Worthington SF | Dunnfield creek (323) | This is one of the most heavily used sections of the A.T. Trail is co-aligned with an old fire road that is still used annually by emergency vehicles. Trail is located in an ecologically sensitive drainage area. Trail is eroding because it is too steep and is not designed to meet the demands of heavy foot traffic. |  | Continuing work to replace cribwalls and control erosion. |  | Build/AddCrib: Rock -cf | 200 | CF | 4870 | 4900 | 93901.65 | 22198.35 | Mid-Atlantic | 1 | 2014 | M | RR-T | Requested |  |  | REQUESTED | 2000 | 323 |  | 2012-01-24 | JDR | Requested
Note on F1: Bundy, Jessica: Parent WO
Note on O1: "AT ID" is the unique ID number assigned to each deficiency found during the Trail Assessment. The "AT ID" can be found on the Google Earth Trail Assessment Disc provided to each club. The first letters of the AT ID indicate what type of deficiency: TR = Tread CS=Campsite SH=Shelter TO=Toilet (Privy) PK=Parking CR=Corridor BR=Bridge

## Completed_Projects
Region | CLUB | FMSS Asset Number | FMSS Equipment # | FMSS WO # | PST WO# | PMIS # | Component | ATC Project # | Work Type | ASSET TYPE | DISTRICT | LOCATION | DEFICIENCY | Trail Assessment "AT ID" (indicate ID number, or range of IDs, project will address) | PROJECT DESCRIPTION | LIST ADDITIONAL MATERIALS AND/OR SERVICES NEEDED | ITEM | QUANTITY | U.O.M | NPS Estimate | NPS Request Amount | ATC Direct Project | ATC Indirect (17.53%) | CREW? | CREW WEEKS | YEAR | Club Priority | Fund Type | NPS Funding Status | ENVIRO COMPLIANCE LEAD AGENCY? | PEPC # | Project Status | Club Estimate | Seg./Tract # | Comments/Other | Last Updated | Updated By | CHANGES
2. MA | 1. NYNJTC | 89649, 89650, 81239 |  | 896057 | 73364 | 77846 |  |  | Demo | BU | NJ | Mussina (307-21) | Incidentally acquired structures |  | Remove structure and restore tract to natural state. | Contract | Structure | 3 | EA | 49486 | 49486 |  |  | No Crew | 0 | 2007 | M | RR-Demo | Requested |  |  | COMPLETE |  | 307-21 |  | 2009-03-10 | BS | Complete
2. MA | 1. NYNJTC | 77147 | 297367 | 893316 |  |  |  |  | Capital | T | NJ, NY/NJ line - Liberty Crn Rd | Rt 94 (303) | Trail goes through seasonally wet area. Existing puncheon is approaching end of life span. |  | Construct/install 500' turnpike between Rt 94 and RR tracks. | Need 500 linear feet of geotextile, 75 cubic yards of fill. | Build/AddTurnpike -lf | 1000 | LF | 21685 | 21000 |  |  | Mid-Atlantic | 2 | 2005 | M | RR-T | Not Requested |  |  | COMPLETE | 10000 | 303 | Done by Club | 2009-03-10 | BS | Complete
2. MA | 1. NYNJTC | 77147 |  | n/a |  |  |  |  | Capital | B | NJ, NY/NJ line - Liberty Crn Rd | Rt 94/Canal Rd | hydrological changes in drainage have resulted in expanded flood zone |  | Extend existing bridge |  | Build/AddLog Bridge -sf | 260 | SF | 21320 | 21320 |  |  | Mid-Atlantic | 1 | 2005 | H | RR-T | Not Requested |  |  | COMPLETE | 18000 |  | Done by Club | 2009-03-10 | BS | Complete
2. MA | 1. NYNJTC | 97860 |  | n/a |  |  |  |  | Capital | P | NJ, NY/NJ line - Liberty Crn Rd | Wawayanda Shelter (302-05) | Pit privy does not meet state sanitation regulations. |  | Install pumpable vault and new outhouse. | 200 gallon concrete vault. 200 board feet of lumber for outhouse. 5 pounds of 8d galvanized common nails. One bundle of shingles. One fuzzy toilet seat. 10 feet of black 6" diameter PVC pipe. One roll of hardware cloth. | Composting Toilet | 1 | EA | 2160.9 | 2160.9 | 1747.7354 | 413.1646 | No Crew | 0 | 2009 | H | RR-OS |  | NJ |  | COMPLETE | 2000 | 302-05 | State installing Clivus composting privy | 2010-02-17 | BS
2. MA | 1. NYNJTC | 95597 | N/F | N/F | N/F | N/F |  |  | CI | P | NJ, Oil City Rd - Brink Rd Shelter | Rutherford Shelter (308) | Overnight site lacks privy. |  | Install moldering privy. | LUMBER: 2"x4"x47" pressure treated (2), 2:x4"x32" PT (3), 2:x4"x18 1/2" PT (2), 2"x4"x81" (2), 2"x4"x64 1/2" (2), 2"x4"x15" (2), 2"x4"x20.5" (2), 2"x4"x32" (1), 2"x4"x22.5" (2), 2"x6"x28" (3), 2"x4"x71" (2), 2"x4"x56.25" (4), 2"x4"x19" (6), 1"x4"x 29.5" (1), 1"x4"x83.5" (2), 1"x6"xx35" 27) Shiplap, 1"x6"x47.75" (26) Shiplap, 1"x6"x27" (3), 1"x4"x40" (2), 1"x6"x80" (6) Shiplap, 5/4"x6"x72" (6), 5/4"x6"x47" (9), 4"x4"x29.5" (6), 2"x4"x72" (2), 2"x4"x42" (3), 4-step stringer (2), 2"x8"x32" (3), 2"x6"x46" (2), 2"x6"x38 3/4" (1), 2"x1.25"x38.75" (1), 2"x4"x38" (2). HARDWARE: metal roofing 3'x5' (1), roofing screws (20), 2" L-brackets (2 pair) and screws, 2"x8" joist hangers (2), 3'x25' 1/4" hardware cloth, 3'x15' fiberglass screening, staples, 3" mending strips (4), 3'x7' metal roofing (2), 30 roofing screws, 3" screws (3 lbs. ), 5d galvanized nails (1/5 lb.), 1 1/4" screws (50), 6" T-hinge (1 pair), Handle (2), Hook and eye (2 pairs), toilet seat. | Composting Toilet | 1 | EA | 2160.9 | 2160.9 | 1747.7354 | 413.1646 | No Crew | 1 | 2009 | H | State | n/a | NJ |  | COMPLETE | 2000 | 308 | Club installing moldering privy | 2013-02-25 | JCB | Project completed by 12/27/11, and moved to the completed project list
2. MA | 1. NYNJTC | 95599 | N/F | 898438 | 9318751 (PST WO still needs to be closed out) | 190640 |  |  | CI | P | NJ, Oil City Rd - Brink Rd Shelter | Gren Anderson shelter (311) | Pit privy does not meet state sanitation regulations. |  | Install moldering privy. | LUMBER: 2"x4"x47" pressure treated (2), 2:x4"x32" PT (3), 2:x4"x18 1/2" PT (2), 2"x4"x81" (2), 2"x4"x64 1/2" (2), 2"x4"x15" (2), 2"x4"x20.5" (2), 2"x4"x32" (1), 2"x4"x22.5" (2), 2"x6"x28" (3), 2"x4"x71" (2), 2"x4"x56.25" (4), 2"x4"x19" (6), 1"x4"x 29.5" (1), 1"x4"x83.5" (2), 1"x6"xx35" 27) Shiplap, 1"x6"x47.75" (26) Shiplap, 1"x6"x27" (3), 1"x4"x40" (2), 1"x6"x80" (6) Shiplap, 5/4"x6"x72" (6), 5/4"x6"x47" (9), 4"x4"x29.5" (6), 2"x4"x72" (2), 2"x4"x42" (3), 4-step stringer (2), 2"x8"x32" (3), 2"x6"x46" (2), 2"x6"x38 3/4" (1), 2"x1.25"x38.75" (1), 2"x4"x38" (2). HARDWARE: metal roofing 3'x5' (1), roofing screws (20), 2" L-brackets (2 pair) and screws, 2"x8" joist hangers (2), 3'x25' 1/4" hardware cloth, 3'x15' fiberglass screening, staples, 3" mending strips (4), 3'x7' metal roofing (2), 30 roofing screws, 3" screws (3 lbs. ), 5d galvanized nails (1/5 lb.), 1 1/4" screws (50), 6" T-hinge (1 pair), Handle (2), Hook and eye (2 pairs), toilet seat. | Composting Toilet | 1 | EA | 2160.9 | 6911 | 5589.615 | 1321.385 | Mid-Atlantic | 1 | 2015 | H | RR-T | Requested |  |  | COMPLETE | 2000 | 311 | Stokes State Forest - was scheduled for 2005 | 2013-02-25 | JCB | Project completed by 12/27/11, and moved to the completed project list
2. MA | 1. NYNJTC | 95600 | N/F | 9320681 | 9323535 (PST WO still needs to be closed out) | 191064 |  |  | CI | P | NJ, Oil City Rd - Brink Rd Shelter | Brinks shelter (314) | Pit privy does not meet state sanitation regulations. |  | Install moldering privy. |  | Composting Toilet | 1 | EA | 2160.9 | 6911 | 5589.615 | 1321.385 | Mid-Atlantic | 1 | 2016 | H | RR-T | Requested |  |  | COMPLETE | 2000 | 314 | Moving ON site from current location also being considered - was 2015 move to 2016 | 2013-02-25 | JCB | Project completed by 12/27/11, and moved to the completed project list
2. MA | 1. NYNJTC | 77154 | 297371 | 712372 | 711339 | 49983 |  |  | DM | T | NJ, Worthington SF | Dunnfield creek (323) | This is one of the most heavily used sections of the A.T. Trail is co-aligned with an old fire road that is still used annually by emergency vehicles. Trail is located in an ecologically sensitive drainage area. Trail is eroding because it is too steep and is not designed to meet the demands of heavy foot traffic. |  | Continuing work to replace cribwalls and control erosion. |  | Build/AddCrib: Rock -cf | 200 | CF | 4870 | 5000 | #N/A | #N/A | Mid-Atlantic | 1 | 2005 | M | RR-T | Requested |  |  | DELETE | 2000 | 323 |  | 2009-03-17 | JDR | DELETE
2. MA | 1. NYNJTC | 77154 | 297371 | 712373 | 711943 | 117930 |  |  | DM | T | NJ, Worthington SF | Dunnfield creek (323) | This is one of the most heavily used sections of the A.T. Trail is co-aligned with an old fire road that is still used annually by emergency vehicles. Trail is located in an ecologically sensitive drainage area. Trail is eroding because it is too steep and is not designed to meet the demands of heavy foot traffic. |  | Continuing work to replace cribwalls and control erosion. |  | Build/AddCrib: Rock -cf | 200 | CF | 4870 | 4750 | #N/A | #N/A | Mid-Atlantic | 1 | 2006 | M | RR-T | Requested |  |  | DELETE | 2000 | 323 |  | 2009-03-10 | BS | DELETE
2. MA | 1. NYNJTC | 77154 |  | n/a |  |  |  | 2040 | DM | T | NJ, Worthington SF | Dunnfield creek (323) | This is one of the most heavily used sections of the A.T. Trail is co-aligned with an old fire road that is still used annually by emergency vehicles. Trail is located in an ecologically sensitive drainage area. Trail is eroding because it is too steep |  | Continuing work to replace cribwalls and control erosion. |  | Build/AddCrib: Rock -cf | 200 | CF | 4870 | 4750 |  |  | Mid-Atlantic | 1 | 2006 | M |  |  |  |  | COMPLETE | 2000 | 323 | Funded by NJDOT and ATPO | 2007-02-19 | JDR | COMPLETE
2. MA | 1. NYNJTC | 95601 |  | 898444 |  | 77836 |  |  | Capital | P | NJ, Worthington SF | Worthington SF/Backpacker Campsite | Current number of privies does not meet demand |  | build more privies |  | Composting Toilet | 2 | EA | 4321.8 | 4321 |  |  | Mid-Atlantic | 1 | 2006 | H | RR-OS | Requested |  |  | COMPLETE |  |  | Done by Club | 2009-03-10 | BS | Complete
2. MA | 1. NYNJTC | 77154 | 297371 | 712374 | 711324 (PST WO still needs to be closed out) | 190640 |  | 2040 | DM | T | NJ, Worthington SF | Dunnfield creek (323) | This is one of the most heavily used sections of the A.T. Trail is co-aligned with an old fire road that is still used annually by emergency vehicles. Trail is located in an ecologically sensitive drainage area. Trail is eroding because it is too steep and is not designed to meet the demands of heavy foot traffic. |  | Continuing work to replace cribwalls and control erosion. |  | Build/AddCrib: Rock -cf | 200 | CF | 4870 | 4750 | 3841.7988 | 4750 | Mid-Atlantic | 1 | 2015 | M | RR-T | Requested |  |  | MOVE | 2000 | 323 |  | 2012-01-25 | JDR | REQUESTED

## Instruction_Sheet
2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020
PAST YEAR(s) (requested in 2010) | CURRENT YEAR (requested in 2011) | OUT | Five Year Plan |  |  |  | NEW
|  | YEAR | (requested
|  | (requested in 2012) | in 2013)
Update Project Status | Confirm Projects | Review Projects | Review and Update | Adjust Project Scopes | Re-Arrange Projects | Remove Completed Projects | Add new Projects
Capital Planning
Five Steps: Fall 2013
The Capital Plan is designed to capture all of the A.T. project needs that may require National Park Service funding or projects that will take place on National Park Service lands and require environmental compliance.
1. Review past year projects (2013 and earlier) and indicate which ones have been completed, which ones need to be moved to another year because they were not done, or which ones can be removed from the list altogether. Once updated, the Plan should only contain projects for 2014 and beyond.
2. Review current year (2014) and next year (2015) projects to confirm scheduled work. Changes to the plan should be brought to the attention of the ATC regional staff as soon as possible so adjustments may be considered. No additional funding is available in these years. Any new or emergency project will need to replace or substitute an existing project on the list.
3. Review all other projects (2016 – 2019) on the list and make any necessary changes. When making changes, consider both the year planned and the scope of work.
4. Add new projects to 2020. 2020 is the only year for which new funding may be available; new projects should be listed here.
5. For each project, please indicate who the land owner is. It is particularly important to note any project that is wholly or partially located on NPS-APPA lands to aid in scheduling compliance reviews.
Use “Enviro Compliance Lead Agency” column to specify land/agency ownership.
6. Indicate the "AT ID" for each project, which is found in Google Earth. This is neccessary to link Capital Plan projects to deficiencies identified during the Trail Assessment. This will also improve reporting of project completion.