## Project_List
Region | CLUB | FMSS Location Number | FMSS Asset # | FMSS WO # | FMSS Parent WO# | PMIS # | Component | ATC Project # | Work Type | ASSET TYPE | DISTRICT | LOCATION | DEFICIENCY | PROJECT DESCRIPTION | LIST ADDITIONAL MATERIALS AND/OR SERVICES NEEDED | ITEM | QUANTITY | U.O.M | NPS Estimate | NPS Request Amount | ATC Direct Project | ATC Indirect (23.64%) | CREW? | CREW WEEKS | YEAR | Club Priority | Fund Type | NPS Funding Status | ENVIRO COMPLIANCE LEAD AGENCY? | PEPC # | Project Status | Club Estimate | Seg./Tract # | Comments/Other | Last Updated | Updated By | CHANGES
2. MA | 1. NYNJTC |  |  | n/a | [5 empty] | ED | Dutchess-Putnam | Dutchess-Putnam | Low neighbor knowledge of AT | Publish neighbor brochure | [5 empty] | 1000 | 808.7997 | 191.2003 | No Crew | 0 | 2010 | M |  | Not Requested | n/a |  | Awaiting Funding | 1000 |  | aprox 15 years ago we had such a brochure. Should be redone to educate corridor neighbors including town officials. 2010 LL Bean grant requested | 2010-01-14 | JPH | Comments
2. MA | 1. NYNJTC | 77139 | 297432 | 712383 | 1479505 | 126217 | A |  | DM | T | Dutchess-Putnam | Route 22 (Swamp River & Hiller Brook) | Wetland crossing | Construct 500 linear feet of raised boardwalk and puncheon through a wetland area near Pawling, New York. It will utilize helical pier technology which has been successfully installed on other sections of the Appalachian Trail and provides for the free-flow of water under the structure reducing impacts on the sensitive wetland area. | Helical piers; 2x10 rough cut oak stringers, 2x8 rough cut planking, spikes | Build/Add Boardwalk | 1600 | LF | NEED | 90000 | 72791.9767 | 17208.0233 | Mid-Atlantic | 5 | 2010 | H | ARRA | FUNDED | ATPO | 25370 |  | 200000 |  | Was pmis# 49983 in 2005 - was 2005, re-estimate costs (DPATMC to get LF figure recalculated), Problem worsening | 2009-03-17 | JDR | Likely '09 Stimulus Funded
2. MA | 1. NYNJTC | [8 empty] | T | Dutchess-Putnam | TNC Easement Relo | trail relocation |  |  | Build/AddTrail: New -lf | 2500 | LF |  |  | 0 | 0 | No Crew | 0 | 2010 |  | n/a | n/a | ATPO | 25372 - need CE |  |  |  | Compliance review done June 2009, waiting NPS clearance to proceed | 2010-01-14 | JPH | WAS 2009, moved to 2010
2. MA | 1. NYNJTC | NEED |  |  |  | NEED |  |  | RM | WS | Dutchess-Putnam | Messerschmidt | Need monthly testing of total coliform | test water systems for TC monthly | Contract services | Water Samples | 12 | EA | NEED | 300 | 242.6399 | 57.3601 | No Crew | 0 | 2010 | H | Base | Requested |  |  |  | 300 |  |  | 2006-11-12 | RSR | NEW PROJECT
2. MA | 1. NYNJTC | 101907 |  |  |  | NEED |  |  | RM | WS | Dutchess-Putnam | Wiley | Need monthly testing of total coliform | test water systems for TC monthly | Contract services | Water Samples | 12 | EA | NEED | 300 | 242.6399 | 57.3601 | No Crew | 0 | 2010 | H | Base | Requested |  |  |  | 300 |  |  | 2006-11-12 | RSR | NEW PROJECT
2. MA | 1. NYNJTC | 101908 |  |  |  | NEED |  |  | RM | WS | Dutchess-Putnam | Morgan Stewart | Need monthly testing of total coliform | test water systems for TC monthly | Contract services | Water Samples | 12 | EA | NEED | 300 | 242.6399 | 57.3601 | No Crew | 0 | 2010 | H | Base | Requested |  |  |  | 300 |  |  | 2006-11-12 | RSR | NEW PROJECT
2. MA | 1. NYNJTC | 101909 |  |  |  | NEED |  |  | RM | WS | Dutchess-Putnam | RPH Cabin | Need monthly testing of total coliform | test water systems for TC monthly | Contract services | Water Samples | 12 | EA | NEED | 300 | 242.6399 | 57.3601 | No Crew | 0 | 2010 | H | Base | Requested |  |  |  | 300 |  |  | 2006-11-12 | RSR | NEW PROJECT
2. MA | 1. NYNJTC |  |  | n/a |  |  |  |  | DM | CR | Dutchess-Putnam | Shenandoah Camp Site | Access Road impassable | Re-grade Road |  |  |  |  | NEED | 1500 | 1213.1996 | 286.8004 | No Crew | 0 | 2010 | L |  | Not Requested |  |  | UNKNOWN |  |  |  | 2009-02-16 | JPH | WAS 2007 MOVE to 2010
2. MA | 1. NYNJTC | 89651, 811221 |  | 896078 | 902143 | 126274 |  |  | Demo | BU | Dutchess-Putnam | Tegzes/Yegella (268-33) | Incidentally acquired structures | Remove structure and restore tract to natural state. | Contract removal of structure | Structure | 2 | EA | 10193 | 10193 | 8244.0958 | 1948.9042 | No Crew | 0 | 2010 | L | RR-Demo | Requested |  |  | In Planning | on demo list | 268-33 | …; delay until Dennis SUP has been renewed | 2006-11-12 | RSR | WAS 2005
2. MA | 1. NYNJTC | 77139 | 384798 | 896082 |  | NEED |  |  | DM | B | Dutchess-Putnam | E. Fishkill (Hosner Mtn Road) | Bridge washout candidate | Repair Bridge |  |  |  |  | NEED | 1500 | 1213.1996 | 286.8004 |  |  | 2010 | M | RR-T | Not Requested |  |  |  | 1500 |  |  | 2006-11-12 | RSR | WAS 2009 MOVE to 2010
2. MA | 1. NYNJTC | 77139 | 297432 | [5 empty] | Capital | T | Dutchess-Putnam | Route 22 (Swamp River & Hiller Brook) | Wetland crossing | Install puncheon | Helical piers; 2x10 rough cut oak stringers, 2x8 rough cut planking, spikes | Build/Add Boardwalk | 1500 | LF |  | 102600 | 82982.8534 | 19617.1466 | Mid-Atlantic | 5 | 2010 | H | RR-S | FUNDED |  |  |  | 200000 |  | 2008 R/R Demo Funds | 2009-02-16 | BS | NEW COMPONENT???
2. MA | 1. NYNJTC | 76726 |  | n/a |  |  |  |  | DM | CR | Dutchess-Putnam | Shenandoah Camp Site | Deteriorated. Old chain link fence | Remove |  |  |  |  | NEED | 500 | 404.3999 | 95.6001 | No Crew | 0 | 2011 | L |  | Not Requested | ATPO |  | UNKNOWN |  |  | Garden used to be enclosed by fence - 2008 or 2009 | 2010-07-23 | JDR | Was 2009, moved to 2011
2. MA | 1. NYNJTC | 88969 |  |  |  | NEED |  |  | Capital | BU | Dutchess-Putnam | Nuclear Lake Garage (269-18) | Decaying walls (roof believed already done) | Repair or replace | [6 empty] | 0 | 0 |  |  | 2011 | H |  | NEED |  |  |  | 8000 |  | Deteriorating - need by 2011: used also for Nuclear Lake dam maintenance equipment | 2009-02-16 | JPH | ADD Project
2. MA | 1. NYNJTC | 77139 | 297432 | 712384 | 711324 | 117913 | A | 2040 | Capital | B | Dutchess-Putnam | Route 22 (Swamp River & Hiller Brook) | Deteriorating bridge- rapidly getting worse. Cribbing all rotted | replace bridge | lumber, hardware | Build/AddLog Bridge -sf | 80 | SF | 6560 | 6560 | 5305.7263 | 1254.2737 | Mid-Atlantic | 1 | 2011 | H | RR-T | Requested |  |  |  | 3000 |  | link to boardwalk project Condition much degraded. | 2009-02-16 | JPH | WAS 2008 MOVED to 2011 - COMBINE with Boardwalk
2. MA | 1. NYNJTC | [9 empty] | Dutchess-Putnam | Route 22 (Swamp River & Hiller Brook) | Continue boardwalk Project |  | 34,500 steel piers, 6,800 lumber, fasteners, 8,000 crew, 4,500 ATC staff (ft), 10,765 ATC OH @ 20% |  |  |  |  | 65000 |  |  | Mid-Atlantic |  | 2011 | H |  | NEED | ATPO |  | Ongoing | 65000 |  | see BS e-mail 12/10/10 | 2010-12-22 | JDR
2. MA | 1. NYNJTC | NEED |  |  |  | NEED |  |  | RM | WS | Dutchess-Putnam | Messerschmidt | Need monthly testing of total coliform | test water systems for TC monthly | Contract services | Water Samples | 12 | EA | NEED | 600 | 485.2798 | 114.7202 | No Crew | 0 | 2011 | H | Base | NEED |  |  |  | 300 |  |  | 2006-11-12 | RSR | NEW PROJECT
2. MA | 1. NYNJTC | 101907 |  |  |  | NEED |  |  | RM | WS | Dutchess-Putnam | Wiley | Need monthly testing of total coliform | test water systems for TC monthly | Contract services | Water Samples | 12 | EA | NEED | 600 | 485.2798 | 114.7202 | No Crew | 0 | 2011 | H | Base | NEED |  |  |  | 300 |  |  | 2006-11-12 | RSR | NEW PROJECT
2. MA | 1. NYNJTC | 101908 |  |  |  | NEED |  |  | RM | WS | Dutchess-Putnam | Morgan Stewart | Need monthly testing of total coliform | test water systems for TC monthly | Contract services | Water Samples | 12 | EA | NEED | 600 | 485.2798 | 114.7202 | No Crew | 0 | 2011 | H | Base | NEED |  |  |  | 300 |  |  | 2006-11-12 | RSR | NEW PROJECT
2. MA | 1. NYNJTC | 101909 |  |  |  | NEED |  |  | RM | WS | Dutchess-Putnam | RPH Cabin | Need monthly testing of total coliform | test water systems for TC monthly | Contract services | Water Samples | 12 | EA | NEED | 600 | 485.2798 | 114.7202 | No Crew | 0 | 2011 | H | Base | NEED |  |  |  | 300 |  |  | 2006-11-12 | RSR | NEW PROJECT
2. MA | 1. NYNJTC | 95589, 95591, 95590 |  |  |  | NEED |  |  | DM | P | Dutchess-Putnam | Wiley, Morgan Stewart & Telephone Pioneer Privies | Privy roof(s) nearing end of life span, privy bodies aging (approx. 20 years old) | Install new asphalt shingles, rehab as needed | New wood frame privy upper portion as needed | Structure | 3 | EA |  |  | 0 | 0 | No Crew | 0 | 2011 | M | RR-OS | NEED |  |  |  | 2000 |  |  | 2009-02-16 | JPH | NEW PROJECT
2. MA | 1. NYNJTC | 81199, 89653 |  | 896076 | 902113 | 126270 |  |  | DM | BU | Dutchess-Putnam | Messerschmitt (273-13) | Incidentally acquired structures | Remove structure and restore tract to natural state. | Contract | Structure | 2 | EA | 21136 | 21136 | 17094.7913 | 4041.2087 | No Crew | 0 | 2012 | L | RR-Demo | Requested | ATPO | NEED | Awaiting Funding | Would like to do in 2008 | 273-13 | vandalism issues. More incidents in 2008 & 2009. Combine with lines 27 and 37 for efficiency? | 2010-07-23 | JDR | Was 2009, moved to 2012
2. MA | 1. NYNJTC | [9 empty] | Dutchess-Putnam | Route 22 (Swamp River & Hiller Brook) | Phase 2 include bridge | [6 empty] | NEED |  |  |  |  | 2012 | H | NEED | FUNDED - 2012 |  |  |  | 60000 |  |  | 2009-06-29 | JDR | ADD Project
2. MA | 1. NYNJTC | 95592 |  |  |  | NEED |  |  | DM | P | Dutchess-Putnam | RPH and Shenandoah campsite (273-01, 13) | Privies aging, filling up | Rehab privies & convert to moldering type | [6 empty] | 0 | 0 |  |  | 2012 | H |  | NEED |  |  |  | 1500 |  |  | 2009-02-16 | JPH | WAS 2009 MOVE to 2012
2. MA | 1. NYNJTC |  |  |  |  | NEED |  |  | RM | OA | Dutchess-Putnam | I-84 overlook (271-22) | Natural succession is taking over the open meadow. | Mow field to maintain meadow. | contract mower/ SUP Holder Charlie Dennis to mow approximately 20 acres | Brush mowing, tractor w/rotary mower | 20 | AC | 4880 | 1200 | 970.5597 | 229.4403 | No Crew | 0 | 2012 | H | CM | NEED | [5 empty] | Cyclic, was done in 2006 and 2009 ($800) | 2010-01-14 | JPH | Was 2011 MOVE to 2012
2. MA | 1. NYNJTC | NEED |  |  |  | NEED |  |  | RM | WS | Dutchess-Putnam | Messerschmidt | Need monthly testing of total coliform | test water systems for TC monthly | Contract services | Water Samples | 12 | EA | NEED | 600 | 485.2798 | 114.7202 | No Crew | 0 | 2012 | H | Base | NEED |  |  |  | 300 |  |  | 2006-11-12 | RSR | NEW PROJECT
2. MA | 1. NYNJTC | 101907 |  |  |  | NEED |  |  | RM | WS | Dutchess-Putnam | Wiley | Need monthly testing of total coliform | test water systems for TC monthly | Contract services | Water Samples | 12 | EA | NEED | 600 | 485.2798 | 114.7202 | No Crew | 0 | 2012 | H | Base | NEED |  |  |  | 300 |  |  | 2006-11-12 | RSR | NEW PROJECT
2. MA | 1. NYNJTC | 101908 |  |  |  | NEED |  |  | RM | WS | Dutchess-Putnam | Morgan Stewart | Need monthly testing of total coliform | test water systems for TC monthly | Contract services | Water Samples | 12 | EA | NEED | 600 | 485.2798 | 114.7202 | No Crew | 0 | 2012 | H | Base | NEED |  |  |  | 300 |  |  | 2006-11-12 | RSR | NEW PROJECT
2. MA | 1. NYNJTC | 101909 |  |  |  | NEED |  |  | RM | WS | Dutchess-Putnam | RPH Cabin | Need monthly testing of total coliform | test water systems for TC monthly | Contract services | Water Samples | 12 | EA | NEED | 600 | 485.2798 | 114.7202 | No Crew | 0 | 2012 | H | Base | NEED |  |  |  | 300 |  |  | 2006-11-12 | RSR | NEW PROJECT
2. MA | 1. NYNJTC | 95198 |  |  |  | NEED |  |  | DM | S | Dutchess-Putnam | Wiley Shelter | Roof and floor reaching end of lifespan | Install new roof and flooring | rolled roofing, roofing nails, drip edge, plywood sheathing, flooring | Rolled roofing | 1 | SQ |  |  | 0 | 0 | No Crew | 0 | 2012 | M | RR-OS | NEED |  |  |  | 2000 |  |  | 2010-01-14 | JPH | NEW PROJECT
2. MA | 1. NYNJTC | 77139 | 297432 | 712382 | 711342 | WAS 62416, NEED NEW |  |  | Capital | CR | Dutchess-Putnam | Schaghticoke MT (265) | Illegal ATV use on A.T. lands. | Install boulder closure. | Contract services. | Build/Add: Gate-each | 2 | EA | 2893.8 | 2900 | 2345.5192 | 554.4808 | No Crew | 0 | 2013 | M | RR-S | NEED |  |  |  | 3000 | 265 | Wait and watch. | 2006-11-12 | RSR | WAS 2005 MOVE to 2013
2. MA | 1. NYNJTC | NEED |  |  |  | NEED |  |  | RM | WS | Dutchess-Putnam | Messerschmidt | Need monthly testing of total coliform | test water systems for TC monthly | Contract services | Water Samples | 12 | EA | NEED | 600 | 485.2798 | 114.7202 | No Crew | 0 | 2013 | H | Base | NEED |  |  |  | 300 |  |  | 2006-11-12 | RSR | NEW PROJECT
2. MA | 1. NYNJTC | 101907 |  |  |  | NEED |  |  | RM | WS | Dutchess-Putnam | Wiley | Need monthly testing of total coliform | test water systems for TC monthly | Contract services | Water Samples | 12 | EA | NEED | 600 | 485.2798 | 114.7202 | No Crew | 0 | 2013 | H | Base | NEED |  |  |  | 300 |  |  | 2006-11-12 | RSR | NEW PROJECT
2. MA | 1. NYNJTC | 101908 |  |  |  | NEED |  |  | RM | WS | Dutchess-Putnam | Morgan Stewart | Need monthly testing of total coliform | test water systems for TC monthly | Contract services | Water Samples | 12 | EA | NEED | 600 | 485.2798 | 114.7202 | No Crew | 0 | 2013 | H | Base | NEED |  |  |  | 300 |  |  | 2006-11-12 | RSR | NEW PROJECT
2. MA | 1. NYNJTC | 101909 |  |  |  | NEED |  |  | RM | WS | Dutchess-Putnam | RPH Cabin | Need monthly testing of total coliform | test water systems for TC monthly | Contract services | Water Samples | 12 | EA | NEED | 600 | 485.2798 | 114.7202 | No Crew | 0 | 2013 | H | Base | NEED |  |  |  | 300 |  |  | 2006-11-12 | RSR | NEW PROJECT
2. MA | 1. NYNJTC | 77139 | 297432 |  |  | NEED |  |  | Capital | T | Dutchess-Putnam | Pawlings Nature Preserve | wet, eroded trail | Install I mile of puncheon |  | Build/AddPuncheon -lf | 5000 | LF | 45600 | 25000 | 20219.9935 | 4780.0065 | SCA | 12 | 2013 | M | PLC | NEED | [5 empty] | In bad shape in 2009, club would like to see done sooner than 2015 | 2010-01-27 | JPH | WAS 2008 MOVE to 2015 - MOVE Earlier
2. MA | 1. NYNJTC | 81121 |  | 896078 |  | NEED |  |  | Demo | BU | Dutchess-Putnam | Hurds Corners, Dover Oak (Yeggela?) (268-38 | Dilapidated springhouse foundation/retention basin and pumphouse foundation. | Remove springhouse foundation/reservoir and pumphouse foundation. | Contract demolition. |  |  |  | 0 | 0 | 0 | 0 | No Crew | 0 | 2014 | M | RR-Demo | NEED |  |  |  | $5K | 268-38 | On Demo List??? | 2010-07-23 | JDR | MOVED to 2014
2. MA | 1. NYNJTC | NEED | [6 empty] | RM | WS | Dutchess-Putnam | Messerschmidt | Need monthly testing of total coliform | test water systems for TC monthly | Contract services | Water Samples | 12 | EA |  |  | 0 | 0 | No Crew | 0 | 2014 | H | Base | NEED |  |  |  | 300 |  |  | 2009-02-20 | JPH | NEW PROJECT
2. MA | 1. NYNJTC | 101907 | [6 empty] | RM | WS | Dutchess-Putnam | Wiley | Need monthly testing of total coliform | test water systems for TC monthly | Contract services | Water Samples | 12 | EA |  |  | 0 | 0 | No Crew | 0 | 2014 | H | Base | NEED |  |  |  | 300 |  |  | 2009-02-20 | JPH | NEW PROJECT
2. MA | 1. NYNJTC | 101908 | [6 empty] | RM | WS | Dutchess-Putnam | Morgan Stewart | Need monthly testing of total coliform | test water systems for TC monthly | Contract services | Water Samples | 12 | EA |  |  | 0 | 0 | No Crew | 0 | 2014 | H | Base | NEED |  |  |  | 300 |  |  | 2009-02-20 | JPH | NEW PROJECT
2. MA | 1. NYNJTC | 101909 | [6 empty] | RM | WS | Dutchess-Putnam | RPH Cabin | Need monthly testing of total coliform | test water systems for TC monthly | Contract services | Water Samples | 12 | EA |  |  | 0 | 0 | No Crew | 0 | 2014 | H | Base | NEED |  |  |  | 300 |  |  | 2009-02-20 | JPH | NEW PROJECT
2. MA | 1. NYNJTC | 81152 |  | 896043 | 902113 | 126270 |  |  | Demo | BU | Dutchess-Putnam | Guardia (271-34) along Hosner Mtn Rd | Incidentally acquired structures | Remove structure and restore tract to natural state. | Contract removal of structure | Structure | 1 | EA | 8347 | 8347 | 6751.0514 | 1595.9486 | No Crew | 0 | 2015 | L | RR-Demo | Requested | ATPO |  | NEED | 1000 | 271-34 | Much of area cleaned up years ago by vols. Masonary mat'l remains to be removed (was 2010, moved to 2015) | 2009-02-19 | JPH
2. MA | 1. NYNJTC | 77139 | 297432 | n/a |  |  |  |  | Capital | T | Dutchess-Putnam | Hoyt Road (266-39) | Trail co-aligned with road and vehicular traffic. Trail not in optimal location. | Relocate Trail off road | Acquire approximately 4.32 acres, upgrade easement to relocate Trail approximately 1/2 mile. | Build/AddTrail: New -lf |  |  | 0 | 0 | 0 | 0 | No Crew | 0 | 2015 | M |  | NEED |  |  | NEW PROJECT | 10000 | 266-39 | NPS owns scenic easement need to up grade to R-O-W | 2010-01-14 | JPH | Was 2004 MOVE to 2015
2. MA | 1. NYNJTC | 77139 | 297432 | n/a |  |  |  |  | Capital | T | Dutchess-Putnam | Harlem Valley Psych Center (267-03, 24) | Illegal ATV use on A.T. lands. | Install boulder and gate closures. | Contract services. | Build/Add: Gate-each | 2 | EA | 2893.8 | 2893.8 | 2340.5047 | 553.2953 | No Crew | 0 | 2015 | H | CM | NEED |  |  | UNKNOWN | 3000 | 267-03, 24 | Massive residential and commercial development adjacent to trail lands to start in 2010 | 2010-01-10 | JPH | WAS 2004 MOVE to 2008 MOVE to 2015
2. MA | 1. NYNJTC |  |  |  |  | NEED |  |  | Capital | PL-bb | Dutchess-Putnam | North side of Route 301 crossing (274) | No public information at major parking area | Rebuild and use former Nuclear Lake parking lot bulletin board | Build bulletin board using design of other recent boards | [5 empty] | 0 | 0 | SCA | 1 | 2015 | M | PLC | Not Requested |  |  | Not on plan | 300 |  |  | 2010-01-14 | JPH
2. MA | 1. NYNJTC | 77139 | 297432 |  |  | NEED |  |  | DM | T | Dutchess-Putnam | Trail south of West Dover Rd. (City Route 20) | Early signs of rot in puncheon | Replace puncheon and substructure | Plastic posts and planking |  | 30 | LF |  |  | 0 | 0 |  |  | 2015 | M |  | NEED | [6 empty] | 2009-02-16 | JPH | WAS 2009 MOVE to 2015
2. MA | 1. NYNJTC | 95592 |  |  |  | NEED |  |  | Capital | P | Dutchess-Putnam | RPH Shelter site (273-01) | Privy gets heavy use | Modify privy to use pumpable tank | [6 empty] | 0 | 0 |  |  | 2015 | M | RR-OS | NEED |  |  |  | 5000 |  |  | 2009-02-20 | JPH | Year - Move to 2015 from 2012
2. MA | 1. NYNJTC |  |  |  |  | NEED |  |  | RM | OA | Dutchess-Putnam | I-84 overlook (271-22) | Natural succession is taking over the open meadow. | Mow field to maintain meadow. | contract mower/ SUP Holder Charlie Dennis to mow approximately 20 acres | Brush mowing, tractor w/rotary mower | 20 | AC | 4880 | 1200 | 970.5597 | 229.4403 | No Crew | 0 | 2015 | H | CM | NEED | [5 empty] | Cyclic, was done in 2006 and 2009 ($800) | 2010-01-14 | JPH | NEW PROJECT
2. MA | 1. NYNJTC | 97586 |  |  |  | NEED |  |  | DM | ECBS | Dutchess-Putnam | Various | Missing NPS boundary monuments | Replace missing NPS boundary monuments | [6 empty] | 0 | 0 |  |  | 2015 | H |  | NEED |  |  |  | Approx 20 monuments at $700 ea |  |  | 2008-04-09 | JPH | NEW PROJECT
2. MA | 1. NYNJTC | 97586 |  |  |  | NEED |  |  | DM | ECBS | Dutchess-Putnam | (1) 270-21 (ROW) (2) 270-22 (3) 0.87ac near Gardiner Hollow Rd (4) ATC property near Hosner Mtn Rd (5) 0.43 ac near Back Ct | Parcels never surveyed | Survey parcels | [6 empty] | 0 | 0 |  |  | 2015 | H |  | NEED | [6 empty] | 2008-04-09 | JPH | NEW PROJECT
2. MA | 1. NYNJTC | 88969 |  |  |  | NEED |  |  | Capital | BU | Dutchess-Putnam | Nuclear Lake [269-18] | Need more space for storage of club tools and supplies. Current space conflicts with Nuclear Lake caretaker's use | Build shed | [6 empty] | 0 | 0 |  |  | 2015 | H |  | NEED |  |  |  | 7000+ |  | Combine with 2011 project | 2010-01-14 | JPH | NEW PROJECT
2. MA | 1. NYNJTC | 77139 | 297432 | [5 empty] | Capital | T | Dutchess-Putnam | Nuclear Lake | Road to Nuke Lake not handicap accessible | Provide Access through gate near caretaker's house | [6 empty] | 0 | 0 | No Crew | 0 | 2015 | M |  | NEED |  |  |  | 500 |  | Gate across entrance road does not allow wheelchairs through | 2009-02-16 | JPH | NEW PROJECT
2. MA | 1. NYNJTC | NEED | [6 empty] | RM | WS | Dutchess-Putnam | Messerschmidt | Need monthly testing of total coliform | test water systems for TC monthly | Contract services | Water Samples | 12 | EA |  |  | 0 | 0 | No Crew | 0 | 2015 | H | Base | NEED |  |  |  | 300 |  |  | 2009-02-20 | JPH | NEW PROJECT
2. MA | 1. NYNJTC | 101907 | [6 empty] | RM | WS | Dutchess-Putnam | Wiley | Need monthly testing of total coliform | test water systems for TC monthly | Contract services | Water Samples | 12 | EA |  |  | 0 | 0 | No Crew | 0 | 2015 | H | Base | NEED |  |  |  | 300 |  |  | 2009-02-20 | JPH | NEW PROJECT
2. MA | 1. NYNJTC | 101908 | [6 empty] | RM | WS | Dutchess-Putnam | Morgan Stewart | Need monthly testing of total coliform | test water systems for TC monthly | Contract services | Water Samples | 12 | EA |  |  | 0 | 0 | No Crew | 0 | 2015 | H | Base | NEED |  |  |  | 300 |  |  | 2009-02-20 | JPH | NEW PROJECT
2. MA | 1. NYNJTC | 101909 | [6 empty] | RM | WS | Dutchess-Putnam | RPH Cabin | Need monthly testing of total coliform | test water systems for TC monthly | Contract services | Water Samples | 12 | EA |  |  | 0 | 0 | No Crew | 0 | 2015 | H | Base | NEED |  |  |  | 300 |  |  | 2009-02-20 | JPH | NEW PROJECT
2. MA | 1. NYNJTC | 77139 | 297432 | [5 empty] | DM | T | Dutchess-Putnam | 268-15 & 16 north of DC 20 | Rotting puncheon | Replace deteriorating puncheon | [6 empty] | 0 | 0 | Mid-Atlantic | 2 | 2015 | H |  | NEED |  |  |  | 1000 |  |  | 2009-02-20 | JPH | NEW PROJECT
2. MA | 1. NYNJTC | 77139 | 297432 | [5 empty] | DM | T | Dutchess-Putnam | Pawling Nature Preserve | Rotting puncheon | Replace deteriorating puncheon | [6 empty] | 0 | 0 | No Crew | 0 | 2015 | H |  | NEED |  |  |  | 1000 |  |  | 2009-02-20 | JPH | NEW PROJECT
2. MA | 1. NYNJTC | 77139 | 297432 | [5 empty] | DM | T | Dutchess-Putnam | S. of Morgan Stewart Shelter (270-07) | Erosion | Install steps | [6 empty] | 0 | 0 | Mid-Atlantic |  | 2015 | H | RR-T | NEED | [6 empty] | 2010-01-10 | JPH | NEW PROJECT
2. MA | 1. NYNJTC |  |  |  |  | NEED |  |  | RM | B | Dutchess-Putnam | Various | Bridge inspections | Arrange for engineer to inspect major foot bridges (e.g. RPH Shelter, Swamp River) | [6 empty] | 0 | 0 |  |  | 2015 | H |  | NEED |  |  |  | Unknown |  | Should be cyclic process; probably 4 or 5 major bridges involved | 2009-02-16 | JPH | NEW PROJECT
2. MA | 1. NYNJTC |  |  | n/a | [5 empty] | CR | Dutchess-Putnam | Putnam County and Nuclear Lake | No Cultural Signage | Design and produce historic material for bulletin boards |  |  |  |  | NEED | 500 | 404.3999 | 95.6001 | No Crew | 0 | 2016 | M |  | Not Requested |  |  | UNKNOWN |  |  | Need OK from NPS for inoculation and hut sites | 2010-01-14 | JPH | Club Priority, NPS Funds?
2. MA | 1. NYNJTC | [9 empty] | Dutchess-Putnam | Revolutionary War inoculation site | Lack of interpretive information | Install interpretive information | [8 empty] | No Crew | 0 | 2016 | M |  | NEED | ATPO |  | NEW PROJECT |  |  |  | 2010-01-14 | JPH | NEW PROJECT
2. MA | 1. NYNJTC | [9 empty] | Dutchess-Putnam | Morgan Stewart Shelter (270-22) | Bear seen in vicinity | Install food storage | [8 empty] | No Crew | 0 | 2016 | M |  | NEED | ATPO |  | NEW PROJECT |  |  |  | 2010-01-14 | JPH | NEW PROJECT
2. MA | 1. NYNJTC | [9 empty] | Dutchess-Putnam | Sweetman Road | Deteriorating puncheon | Replace puncheon | [10 empty] | 2016 | H |  | NEED | ATPO |  | NEW PROJECT |  |  |  | 2010-01-14 | JPH | NEW PROJECT
2. MA | 1. NYNJTC | [9 empty] | Dutchess-Putnam | Nuclear Lake (269-18) | Emergency access to caretaker house and lake can be blocked by parked cars | Redesign parking area | [10 empty] | 2016 | H |  | NEED | ATPO |  | NEW PROJECT |  |  |  | 2010-01-14 | JPH | NEW PROJECT
2. MA | 1. NYNJTC | [9 empty] | Dutchess-Putnam | Yegalla barn (268-33) | Structural deficiencies, including floor joists | Evaluate and repair | [10 empty] | 2016 | H |  | NEED | ATPO |  | NEW PROJECT |  | 268-33 |  | 2010-01-14 | JPH | NEW PROJECT
2. MA | 1. NYNJTC |  |  |  |  | NEED |  |  | DM | CR | Dutchess-Putnam | Morgan Stewart (270-22) | Illegal ATV use on A.T. lands | Install iceberged boulders | Contract services |  | 2 | EA |  |  | 0 | 0 | No Crew | 0 | 2016 | H | CM | NEED | ATPO | CE-PA |  |  |  | Needs lower gate landowner permission | 2010-01-14 | JPH | NEW PROJECT

## Completed_Projects
Region | CLUB | FMSS Asset Number | FMSS Equipment # | FMSS WO # | FMSS Parent WO# | PMIS # | Component | ATC Project # | Work Type | ASSET TYPE | DISTRICT | LOCATION | DEFICIENCY | PROJECT DESCRIPTION | LIST ADDITIONAL MATERIALS AND/OR SERVICES NEEDED | ITEM | QUANTITY | U.O.M | NPS Estimate | NPS Request Amount | ATC Direct Project | ATC Indirect (17.53%) | CREW? | CREW WEEKS | YEAR | Club Priority | Fund Type | NPS Funding Status | ENVIRO COMPLIANCE LEAD AGENCY? | PEPC # | Project Status | Club Estimate | Seg./Tract # | Comments/Other | Last Updated | Updated By | CHANGES
2. MA | 1. NYNJTC | 77139 |  | n/a |  |  |  |  | Capital | T | Dutchess-Putnam | Long Hill Road (273-09) | Illegal dumping on A.T. lands. | Install boulder closure. | Purchase and install boulder closures | Build/Add: Gate-each | 1 | EA | 1446.9 | 1446.9 |  |  | No Crew | 0 | 2004 | M | CM |  |  |  | COMPLETE | 1000 | 273-09 | E. Fishkill supplied boulders | 2008-04-09 | JPH | Project Status, Comments
2. MA | 1. NYNJTC | 81346 | 280957 | 895255 | 711342 | 62416 |  |  | DM | BU | Dutchess-Putnam | Nuclear Lake | roof is in disrepair | replace house and garage roof, gutters and leak damaged sheetrock | Asphalt shingles, felt paper, sheathing, drip edge, nails, gutters and downspouts | asphalt shingles | 1276 | SF | NEED | 12000 |  |  | No Crew | 0 | 2005 | H | RR-T2 | Requested |  |  | COMPLETE | na |  | Roof leaking for over a year. | 2005-01-14 | JDR | NO CHANGE
2. MA | 1. NYNJTC | 81346 | 384591 | 895260 | 711342 | 62416 |  |  | Legislative | BU | Dutchess-Putnam | Nuclear Lake | Well does not meet Clean Water Act standards | Install new well | Contract service to abandon two existing wells and drill new well and connect service to house | Well | 1 | EA | NEED | 10000 |  |  | No Crew | 0 | 2005 | H | RR-T2 | Requested |  |  | COMPLETE |  |  |  | 2005-01-14 | JDR | NO CHANGE
2. MA | 1. NYNJTC | 95355 |  | n/a |  | 77835 |  |  | Legislative | S | Dutchess-Putnam | RPH Cabin (272-23) | Water system does meet requirements of the Safe Drinking Water Act. | Replace water pump, extend well casing and back fill concrete block pump house. | Contract services. | Handpump | 1 | EA | NEED | 8000 |  |  | No Crew | 0 | 2005 | H | RR-OS | Requested |  |  | COMPLETE | 0 | 272-23 |  | 2006-02-02 | JDR | COMPLETE
2. MA | 1. NYNJTC | 77139 | 297432 | 822568 |  | 108312 | A |  | Capital | T | Dutchess-Putnam | Bear Mountain (278-279) | [7 empty] | 25000 |  |  | SCA | 12 | 2006 | M | PLC | Requested |  |  | COMPLETE |  |  | Was Pawlings, used at Bear Mountian | 2006-11-12 | RSR | CHANGE DESCRIPTION
2. MA | 1. NYNJTC | 81501 |  | 896024 |  | NEED |  | 2375 |  | OA | Dutchess-Putnam | I-84 overlook (271-22) | Natural succession is taking over the open meadow. | Mow field to maintain meadow. | contract mower/ SUP Holder Charlie Dennis to mow approximately 20 acres | Brush mowing, tractor w/rotary mower | 20 | AC | 4880 | 1200 |  |  | No Crew | 0 | 2006 | H | CM | NEED |  |  | COMPLETE | 1000 | 271-22 | Cyclic, was done in 2006 | 2006-11-12 | RSR | COMPLETE
2. MA | 1. NYNJTC | 77139 |  | 898456 | [5 empty] | T | Dutchess-Putnam | Various | Deteriorating trailhead B-boards | Replace deteriorated trailhead sign boards | Roof - cedar shakes 8' x 3', 2 12 foot logs 6-8 inches in diameter | Build/AddBulletin Board -each | 6 | EA | 5709.78 | 5000 |  |  | No Crew | 0 | 2006 | H |  |  |  |  | COMPLETE | 2400 |  | 3 built by Boy Scouts and 3 by DPATMC volunteers - 6 now installed, need populating with information & covers installed; local funding | 2006-11-12 | RSR | COMPLETE
2. MA | 1. NYNJTC | 81501 |  | 898455 | [5 empty] | OA | Dutchess-Putnam | Route 52 | Open area subject to succession | Mow field every 2-3 years |  | Brush mowing, tractor w/rotary mower | 20 | AC | 4880 | 1200 |  |  | No Crew | 0 | 2006 | H | CM |  |  |  | COMPLETE | 1000 |  | Done in 2006 | 2008-04-09 | JPH | Project Status, Comments
2. MA | 1. NYNJTC | 77139 |  | n/a |  | NEED |  |  |  | WS | Dutchess-Putnam | Messerschmidt | Need monthly testing of total coliform | test water systems for TC monthly | Contract services | Water Samples | 12 | EA | NEED | 600 |  |  | No Crew | 0 | 2007 | H | Base | NEED |  |  | COMPLETE | 300 |  | Done by volunteers | 2009-02-16 | JPH | COMPLETE
2. MA | 1. NYNJTC | 101907 |  | 896048 |  | NEED |  |  |  | WS | Dutchess-Putnam | Wiley | Need monthly testing of total coliform | test water systems for TC monthly | Contract services | Water Samples | 12 | EA | NEED | 600 |  |  | No Crew | 0 | 2007 | H | Base | NEED |  |  | COMPLETE | 300 |  | Done by volunteers | 2009-02-16 | JPH | COMPLETE
2. MA | 1. NYNJTC | 101908 |  | 896050 |  | NEED |  |  |  | WS | Dutchess-Putnam | Morgan Stewart | Need monthly testing of total coliform | test water systems for TC monthly | Contract services | Water Samples | 12 | EA | NEED | 600 |  |  | No Crew | 0 | 2007 | H | Base | NEED |  |  | COMPLETE | 300 |  | Done by volunteers | 2009-02-16 | JPH | COMPLETE
2. MA | 1. NYNJTC | 101909 |  | 86055 |  | NEED |  |  |  | WS | Dutchess-Putnam | RPH Cabin | Need monthly testing of total coliform | test water systems for TC monthly | Contract services | Water Samples | 12 | EA | NEED | 600 |  |  | No Crew | 0 | 2007 | H | Base | NEED |  |  | COMPLETE | 300 |  | Done by volunteers | 2009-02-16 | JPH | COMPLETE
2. MA | 1. NYNJTC | 95200 |  | 898465 | 712630 | 77843 | A |  | DM | S | Dutchess-Putnam | Depot Hill Road/Morgan Stewart Shelter | Roof is nearing the end of its life span. | Install new asphalt shingles | rolled roofing, roofing nails, drip edge, plywood sheathing | Rolled Roofing | 10 | SQ | 1004.5 | 1004.5 |  |  | No Crew | 0 | 2007 | M | RR-OS | Requested |  |  | COMPLETE | 1000 |  |  | 2008-04-09 | JPH | Project Status
2. MA | 1. NYNJTC | 77139 | 384797 | 896068 |  | NEED |  |  |  | B | Dutchess-Putnam | Old Rt. 55 (Whaley Lake Stream) | Deteriorating Bridge | Replace Bridge |  |  |  |  | NEED | 3000 |  |  |  |  | 2007 | H | RR-T | NEED |  |  | COMPLETE | 3000 |  | Accelerate funding; needs project review | 2008-04-09 | JPH | Project Status
2. MA | 1. NYNJTC |  |  |  |  | NEED |  |  |  | T | Dutchess-Putnam | Chapman Road | Wet, eroded trail | Puncheon | Plastic posts and planking | Build/Add puncheon | 100 | LF |  | 4750 |  |  | Mid-Atlantic | 1 | 2007 | M | RR-T | NEED |  |  | COMPLETE |  |  | Done 9/07 | 2008-04-09 | JPH | Project Status, Comments
2. MA | 1. NYNJTC |  |  |  |  | NEED |  |  |  | S | Dutchess-Putnam | Telephone Pioneers Shelter | Roof is nearing the end of its life span | Install new wood as needed, asphalt shingles, & drip edge | rolled roofing, roofing nails, drip edge, plywood sheathing | Rolled roofing | 10 | SQ |  |  |  |  | No Crew | 0 | 2007 | M | RR-OS | NEED |  |  | COMPLETE | 1000 |  | Morgan Stewart roof done 2006--donated shingles | 2008-04-09 | JPH | Project Status
2. MA | 1. NYNJTC | 81346 |  | 836499 |  | 119475 |  |  | DM | BU | Dutchess-Putnam | Nuclear Lake | Inadequate access road and deteriorating caretaker house |  | Contract |  | 1 | EA | 252023.09 | 252023.09 |  |  | No Crew | 0 | 2008 | H | Dam Safety | FUNDED |  |  | COMPLETE |  |  | To be completed with BOR Agreement | 2009-02-16 | JPH | COMPLETE
2. MA | 1. NYNJTC |  |  |  |  | NEED |  |  |  | B | Dutchess-Putnam | Yegella Farm (268-38) | Deteriorating stiles and bridge | Replace stiles and bridge | [10 empty] | 2008 | H |  | NEED |  |  | COMPLETE | 400 |  | Likely local funding | 2009-02-16 | JPH | COMPLETE
2. MA | 1. NYNJTC |  |  |  |  | NEED |  |  |  | WS | Dutchess-Putnam | Messerschmidt | Need monthly testing of total coliform | test water systems for TC monthly | Contract services | Water Samples | 12 | EA | NEED | 600 |  |  | No Crew | 0 | 2008 | H | Base | NEED |  |  | COMPLETE | 300 |  |  | 2009-02-16 | JPH | COMPLETE
2. MA | 1. NYNJTC |  |  |  |  | NEED |  |  |  | WS | Dutchess-Putnam | Wiley | Need monthly testing of total coliform | test water systems for TC monthly | Contract services | Water Samples | 12 | EA | NEED | 600 |  |  | No Crew | 0 | 2008 | H | Base | NEED |  |  | COMPLETE | 300 |  |  | 2009-02-16 | JPH | COMPLETE
2. MA | 1. NYNJTC |  |  |  |  | NEED |  |  |  | WS | Dutchess-Putnam | Morgan Stewart | Need monthly testing of total coliform | test water systems for TC monthly | Contract services | Water Samples | 12 | EA | NEED | 600 |  |  | No Crew | 0 | 2008 | H | Base | NEED |  |  | COMPLETE | 300 |  |  | 2009-02-16 | JPH | COMPLETE
2. MA | 1. NYNJTC |  |  |  |  | NEED |  |  |  | WS | Dutchess-Putnam | RPH Cabin | Need monthly testing of total coliform | test water systems for TC monthly | Contract services | Water Samples | 12 | EA | NEED | 600 |  |  | No Crew | 0 | 2008 | H | Base | NEED |  |  | COMPLETE | 300 |  |  | 2009-02-16 | JPH | COMPLETE
2. MA | 1. NYNJTC |  |  |  |  | NEED |  |  |  | T | Dutchess-Putnam | Trail south of Penny Rd. to Nuclear Lake boundary (269-01) | Rotting puncheon over beaver swamp | Replace puncheon and substructure | Plastic posts and planking |  | 75 | LF | [6 empty] | 2008 | H |  | NEED |  |  | COMPLETE | 600 |  |  | 2009-02-16 | JPH | COMPLETE
2. MA | 1. NYNJTC |  |  |  |  | NEED |  |  |  | P | Dutchess-Putnam | Wiley & Telephone Pioneer Privies | Long term problem with finding appropriate location for privy hole | Convert to moldering privies | Wood and hardware cloth (match materials list used for Morgan Stewart privy) | [7 empty] | No Crew | 0 | 2008 | M |  | NEED |  |  | COMPLETE | 600 |  |  | 2009-02-16 | JPH | COMPLETE
2. MA | 1. NYNJTC | 81346 |  | 836483 |  | 126223 | A |  | DM | BU | Dutchess-Putnam | Nuclear Lake | potholes in access rd | repair holes in access rd | Dump truck full of stone, equipment to spread it around. One truckload of 2-3" stone should be sufficient. 20 tons (1.4 tons per CY) | Borrow, spread w/dozer, crushed stone, 1/2" |  | CY |  | 56140.18 |  |  | No Crew | 0 | 2008 | H | RR-S | Requested |  |  | COMPLETE |  |  | May hamper emergency vehicles | 2009-03-17 | JDR | Remove PMIS Request
2. MA | 1. NYNJTC | 77139 | 297432 | 712363 | 711324 | 117913 | A | 2040 | Capital | B | Dutchess-Putnam | RPH Cabin | Bridge is subject to washout | replace or rebuild existing bridge | lumber, hardware | Build/AddLog Bridge -sf | 60 | SF | 4920 | 4920 |  |  | Mid-Atlantic | 1 | 2008 | M | RR-T | Requested |  |  | COMPLETE | 1500 |  | Done 7/07 | 2008-04-09 | JPH | Project Status, Comments
2. MA | 1. NYNJTC |  |  |  |  | NEED |  | 2040 |  | T | Dutchess-Putnam | Swamp at Sweetman | Wet, eroded trail | Puncheon | Plastic posts and planking | Build/Add puncheon | 100 | LF |  | 4750 |  |  | Mid-Atlantic | 1 | 2008 | M | RR-T | Not Requested |  |  | COMPLETE |  |  | Done 7/07 | 2008-04-09 | JPH | Project Status, Comments
2. MA | 1. NYNJTC |  |  |  |  | NEED |  |  |  | T | Dutchess-Putnam | Old Route 55 to Whaley Lake stream bridge (269-14) | Boggy wet area | Build puncheon | Plastic posts and planking |  | 300 | LF |  |  |  |  | SCA | 1 | 2008 | M | PLC | NEED |  |  | COMPLETE | 2400 |  | Done 10/07 | 2008-04-09 | JPH | Project Status, Comments
2. MA | 1. NYNJTC | 101909 |  |  |  | NEED |  |  | RM | WS | Dutchess-Putnam | RPH Cabin | Need monthly testing of total coliform | test water systems for TC monthly | Contract services | Water Samples | 12 | EA | NEED | 600 | 485.2798 | 114.7202 | No Crew | 0 | 2009 | H | none | n/a | ATPO | CE | COMPLETE | 300 |  | Volunteers plan to continue to do | 2010-01-14 | JPH
2. MA | 1. NYNJTC | 101908 |  |  |  | NEED |  |  | RM | WS | Dutchess-Putnam | Morgan Stewart | Need monthly testing of total coliform | test water systems for TC monthly | Contract services | Water Samples | 12 | EA | NEED | 600 | 485.2798 | 114.7202 | No Crew | 0 | 2009 | H | none | n/a | ATPO | CE | COMPLETE | 300 |  | Volunteers plan to continue to do | 2010-01-14 | JPH
2. MA | 1. NYNJTC | 101907 |  |  |  | NEED |  |  | RM | WS | Dutchess-Putnam | Wiley | Need monthly testing of total coliform | test water systems for TC monthly | Contract services | Water Samples | 12 | EA | NEED | 600 | 485.2798 | 114.7202 | No Crew | 0 | 2009 | H | none | n/a | ATPO | CE | COMPLETE | 300 |  | Volunteers plan to continue to do | 2010-01-14 | JPH
2. MA | 1. NYNJTC | NEED |  |  |  | NEED |  |  | RM | WS | Dutchess-Putnam | Messerschmidt | Need monthly testing of total coliform | test water systems for TC monthly | Contract services | Water Samples | 12 | EA | NEED | 600 | 485.2798 | 114.7202 | No Crew | 0 | 2009 | H | none | n/a | ATPO |  | COMPLETE | 300 |  | Volunteers plan to continue to do | 2010-01-14 | JPH
2. MA | 1. NYNJTC |  |  |  |  | NEED |  |  | RM | OA | Dutchess-Putnam | I-84 overlook (271-22) | Natural succession is taking over the open meadow. | Mow field to maintain meadow. | contract mower/ SUP Holder Charlie Dennis to mow approximately 20 acres | Brush mowing, tractor w/rotary mower | 20 | AC | 4880 | 1200 | 970.5597 | 229.4403 | No Crew | 0 | 2009 | H | CM | NEED | ATPO | NA | COMPLETE |  |  | Cyclic, was done in 2006 | 2010-01-14 | JPH | NEW PROJECT
2. MA | 1. NYNJTC | 89649, 89650, 81239 |  | 896057 | 73364 | 77846 |  |  | Demo | BU | NJ | Mussina (307-21) | Incidentally acquired structures | Remove structure and restore tract to natural state. | Contract | Structure | 3 | EA | 49486 | 49486 |  |  | No Crew | 0 | 2007 | M | RR-Demo | Requested |  |  | COMPLETE |  | 307-21 |  | 2009-03-10 | BS | Complete
2. MA | 1. NYNJTC | 77147 | 297367 | 893316 |  |  |  |  | Capital | T | NJ, NY/NJ line - Liberty Crn Rd | Rt 94 (303) | Trail goes through seasonally wet area. Existing puncheon is approaching end of life span. | Construct/install 500' turnpike between Rt 94 and RR tracks. | Need 500 linear feet of geotextile, 75 cubic yards of fill. | Build/AddTurnpike -lf | 1000 | LF | 21685 | 21000 |  |  | Mid-Atlantic | 2 | 2005 | M | RR-T | Not Requested |  |  | COMPLETE | 10000 | 303 | Done by Club | 2009-03-10 | BS | Complete
2. MA | 1. NYNJTC | 77147 |  | n/a |  |  |  |  | Capital | B | NJ, NY/NJ line - Liberty Crn Rd | Rt 94/Canal Rd | hydrological changes in drainage have resulted in expanded flood zone | Extend existing bridge |  | Build/AddLog Bridge -sf | 260 | SF | 21320 | 21320 |  |  | Mid-Atlantic | 1 | 2005 | H | RR-T | Not Requested |  |  | COMPLETE | 18000 |  | Done by Club | 2009-03-10 | BS | Complete
2. MA | 1. NYNJTC | 97860 |  | n/a |  |  |  |  | Capital | P | NJ, NY/NJ line - Liberty Crn Rd | Wawayanda Shelter (302-05) | Pit privy does not meet state sanitation regulations. | Install pumpable vault and new outhouse. | 200 gallon concrete vault. 200 board feet of lumber for outhouse. 5 pounds of 8d galvanized common nails. One bundle of shingles. One fuzzy toilet seat. 10 feet of black 6" diameter PVC pipe. One roll of hardware cloth. | Composting Toilet | 1 | EA | 2160.9 | 2160.9 | 1747.7354 | 413.1646 | No Crew | 0 | 2009 | H | RR-OS |  | NJ |  | COMPLETE | 2000 | 302-05 | State installing Clivus composting privy | 2010-02-17 | BS
2. MA | 1. NYNJTC | 77154 | 297371 | 712372 | 711339 | 49983 |  |  | DM | T | NJ, Worthington SF | Dunnfield creek (323) | This is one of the most heavily used sections of the A.T. Trail is co-aligned with an old fire road that is still used annually by emergency vehicles. Trail is located in an ecologically sensitive drainage area. Trail is eroding because it is too steep and is not designed to meet the demands of heavy foot traffic. | Continuing work to replace cribwalls and control erosion. |  | Build/AddCrib: Rock -cf | 200 | CF | 4870 | 5000 | 4043.9987 | 956.0013 | Mid-Atlantic | 1 | 2005 | M | RR-T | Requested |  |  | DELETE | 2000 | 323 |  | 2009-03-17 | JDR | DELETE
2. MA | 1. NYNJTC | 77154 | 297371 | 712373 | 711943 | 117930 |  |  | DM | T | NJ, Worthington SF | Dunnfield creek (323) | This is one of the most heavily used sections of the A.T. Trail is co-aligned with an old fire road that is still used annually by emergency vehicles. Trail is located in an ecologically sensitive drainage area. Trail is eroding because it is too steep and is not designed to meet the demands of heavy foot traffic. | Continuing work to replace cribwalls and control erosion. |  | Build/AddCrib: Rock -cf | 200 | CF | 4870 | 4750 | 3841.7988 | 908.2012 | Mid-Atlantic | 1 | 2006 | M | RR-T | Requested |  |  | DELETE | 2000 | 323 |  | 2009-03-10 | BS | DELETE
2. MA | 1. NYNJTC | 77154 |  | n/a |  |  |  | 2040 | DM | T | NJ, Worthington SF | Dunnfield creek (323) | This is one of the most heavily used sections of the A.T. Trail is co-aligned with an old fire road that is still used annually by emergency vehicles. Trail is located in an ecologically sensitive drainage area. Trail is eroding because it is too steep | Continuing work to replace cribwalls and control erosion. |  | Build/AddCrib: Rock -cf | 200 | CF | 4870 | 4750 |  |  | Mid-Atlantic | 1 | 2006 | M |  |  |  |  | COMPLETE | 2000 | 323 | Funded by NJDOT and ATPO | 2007-02-19 | JDR | COMPLETE
2. MA | 1. NYNJTC | 95601 |  | 898440 |  | 77836 |  |  | Capital | P | NJ, Worthington SF | Worthington SF/Backpacker Campsite | Current number of privies does not meet demand | build more privies |  | Composting Toilet | 2 | EA | 4321.8 | 4321 |  |  | Mid-Atlantic | 1 | 2006 | H | RR-OS | Requested |  |  | COMPLETE |  |  | Done by Club | 2009-03-10 | BS | Complete
2. MA | 1. NYNJTC | 77145 |  | n/a |  |  |  | 2040 | Capital | T | Orange-Rockland | Bear Mountain (278-279) | This section of Trail is the most heavily used of the entire A.T. Thin soils, steep grade and extremely heavy use have resulted in severely eroded footpath that exceeds 30 feet in width for approximately 2 miles. | Relocate approximately 2 miles of the Trail. Construct 2 miles of stone crib wall and harden footpath. | One thousand tons of stone. One thousand tons of crushed fill. | Build/AddTrail: New -lf | 1000 | LF | NEED | 50000 |  |  | Mid-Atlantic | 10 | 2004 | H | RR-T |  |  |  | COMPLETE | $500K | 278-279 |  | 2007-02-19 | JDR | NO CHANGE
2. MA | 1. NYNJTC | 77145 | 297433 | 712365 |  | 108299 |  | FM-101 | Capital | T | Orange-Rockland | Bear Mountain (278-279) | This section of Trail is the most heavily used of the entire A.T. Thin soils, steep grade and extremely heavy use have resulted in severely eroded footpath that exceeds 30 feet in width for approximately 2 miles. | Relocate approximately 2 miles of the Trail. Construct 2 miles of stone crib wall and harden footpath. | One thousand tons of stone. One thousand tons of crushed fill. | Build/AddTrail: New -lf | 3400 | LF | 26010 | 26000 |  |  | Mid-Atlantic | 10 | 2005 | H | RR-S | Requested |  |  | COMPLETE | $500K | 278-279 |  | 2007-02-19 | JDR | NO CHANGE
2. MA | 1. NYNJTC | 77145 | 297433 | 712366 |  | 108299 |  | FM-101 | Capital | T | Orange-Rockland | Bear Mountain (278-279) | This section of Trail is the most heavily used of the entire A.T. Thin soils, steep grade and extremely heavy use have resulted in severely eroded footpath that exceeds 30 feet in width for approximately 2 miles. | Relocate approximately 2 miles of the Trail. Construct 2 miles of stone crib wall and harden footpath. | One thousand tons of stone. One thousand tons of crushed fill. | Build/AddTrail: New -lf | 1000 | LF | NEED | 156520 |  |  | Mid-Atlantic | 10 | 2006 | H | RR-S | Requested |  |  | COMPLETE | $500K | 278-279 |  | 2007-02-19 | JDR | COMPLETE
2. MA | 1. NYNJTC | 77145 | 297433 | 712367 |  | 108304 | A | FM-101 | Capital | T | Orange-Rockland | Bear Mountain (278-279) | This section of Trail is the most heavily used of the entire A.T. Thin soils, steep grade and extremely heavy use have resulted in severely eroded footpath that exceeds 30 feet in width for approximately 2 miles. | Relocate approximately 2 miles of the Trail. Construct 2 miles of stone crib wall and harden footpath. | One thousand tons of stone. One thousand tons of crushed fill. | Build/AddTrail: New -lf | 1000 | LF |  | 25000 |  |  | SCA | 4 | 2006 | H | PLC | Requested |  |  | COMPLETE | $500K | 278-279 |  | 2007-02-19 | JDR | COMPLETE
2. MA | 1. NYNJTC | 77145 | 297433 | 712368 |  | 108299 | C |  | Capital | T | Orange-Rockland | Bear Mountain (278-279) | This section of Trail is the most heavily used of the entire A.T. Thin soils, steep grade and extremely heavy use have resulted in severely eroded footpath that exceeds 30 feet in width for approximately 2 miles. | Relocate approximately 2 miles of the Trail. Construct 2 miles of stone crib wall and harden footpath. | One thousand tons of stone. One thousand tons of crushed fill. | Build/AddTrail: New -lf | 1000 | LF | NEED | 186616 |  |  | Mid-Atlantic | 10 | 2007 | H | RR-S | Requested |  |  | COMPLETE | $500K | 278-279 |  | 2009-01-21 | BS | Complete
2. MA | 1. NYNJTC | 77145 | 297433 | 713413 |  | 108304 | B |  | Capital | T | Orange-Rockland | Bear Mountain (278-279) | This section of Trail is the most heavily used of the entire A.T. Thin soils, steep grade and extremely heavy use have resulted in severely eroded footpath that exceeds 30 feet in width for approximately 2 miles. | Relocate approximately 2 miles of the Trail. Construct 2 miles of stone crib wall and harden footpath. | One thousand tons of stone. One thousand tons of crushed fill. | Build/AddTrail: New -lf | 1000 | LF | NEED | 25000 |  |  | SCA | 4 | 2007 | H | PLC | Requested |  |  | COMPLETE | $500K | 278-279 |  | 2009-01-21 | BS | Complete
2. MA | 1. NYNJTC | 77145 | 297433 | 893323 |  | 126228 | A | 2082 | Capital | T | Orange-Rockland | Bear Mountain (278-279) | This section of Trail is the most heavily used of the entire A.T. Thin soils, steep grade and extremely heavy use have resulted in severely eroded footpath that exceeds 30 feet in width for approximately 2 miles. | Relocate approximately 2 miles of the Trail. Construct 2 miles of stone crib wall and harden footpath. | One thousand tons of stone. One thousand tons of crushed fill. | Build/AddTrail: New -lf | 1000 | LF | NEED | 69015 | 58721.1776 | 10293.8224 | Mid-Atlantic | 10 | 2008 | H | RR-S | FUNDED |  |  | COMPLETE | $500K | 278-279 |  | 2009-01-21 | BS | Complete
2. MA | 1. NYNJTC | 77145 | 297433 | 712369 | 711325 | 126228 | B | 2082 | Capital | T | Orange-Rockland | Bear Mountain (278-279) | This section of Trail is the most heavily used of the entire A.T. Thin soils, steep grade and extremely heavy use have resulted in severely eroded footpath that exceeds 30 feet in width for approximately 2 miles. | Relocate approximately 2 miles of the Trail. Construct 2 miles of stone crib wall and harden footpath. | One thousand tons of stone. One thousand tons of crushed fill. | Build/AddTrail: New -lf | 1000 | LF | NEED | 169913.55 | 137426.0353 | 32487.5147 | Mid-Atlantic | 10 | 2009 | H | RR-S | Requested | NY |  | COMPLETE | $500K | 278-279 | WAS PMIS # 117914 RR-T | 2009-02-04 | JDR | NO CHANGE
2. MA | 1. NYNJTC | 77145 |  |  | 3059462 | 154939 | A |  |  |  | Orange-Rockland | Bear Mountain (278-279) |  | This project will build upon the significant accomplishments of earlier trail rehabilitation projects in the Bear Mountain area of New York. This project constitutes the sixth phase of the project and involves the restoration of a section of approximately 1,000 linear feet of existing trail. A combination of volunteers and professionally led trail crews will complete the work. |  |  | 1000 | LF | 90000 | 90000 | 72791.9767 | 17208.0233 |  |  | 2010 | H | ARRA | FUNDED | NY State/ATPO | 26378 | COMPLETE |  |  |  | 2011-01-06 | JDR | ADDED for ARRA
2. MA | 1. NYNJTC | NEED | [6 empty] | Capital | B | Orange-Rockland | Little Dam Lake outlet (E. Mombasha Rd) (282) | Abutments have failed. Bridge structure is approaching the end of its life span. | Replace with step stones | [6 empty] | 0 | 0 | No Crew | 0 | 2010 | H |  |  |  |  | COMPLETE |  | 282-05 | May need to addresses sooner as safety issue: current bridge unlikely to last 7 years: 6x6 PT lumber abutments have failed, designing engineer suggests replacement of entire bridge | 2010-12-22 | BS | Completed by club